## Sheet1
ID | Work Item Type | Created Date | Feature Title | User Story Title | Assigned To | State | AskIT Enhancement Number | Customer Name | Iteration Path | Area Path | Level of Effort | Story Points (0 - 99) | Value (0 - 99) | Priority (0 - 4) | Target Date | Business Value (0 - 999) | Cleaned Feature Title | Cleaned User Story Title
17021 | Feature | 2019-07-01 09:44 | Add UMD for "full de-ice event" dates into flight model |  |  | New | ENHC0010862 | Matthew Broderick |  | \ | high | 69 |  | 2 |  |  | Add UMD "full de-ice event" dates flight model
27621 | Feature | 2023-02-02 09:49 | Compensation rates are not populating in Concessions reports. |  | Anthony | Active | ENHC0014455 | Branden Flowers | Rose | \ | medium | 42 |  | 2 | 2025-01-04 |  | Compensation rates populating Concessions reports.
30708 | User Story | 2024-01-04 09:29 |  | Finance Source - Develop to pull compensation rates | Anthony | On Hold | ENHC0014455 |  | Poppy | \ | low | 20 |  | 0 | 2024-11-30 |  |  | Finance Source - Develop pull compensation rates
28848 | Feature | 2023-06-20 11:49 | Migrate Pena traffic data from source to prod |  | Anthony | On Hold | ENHC0014783 | Chelesa Clinton |  | \ | high | 85 |  | 3 |  |  | Migrate Pena traffic data source prod
32169 | User Story | 2024-04-17 08:31 |  | Pena Traffic Data in BI | Anthony | Closed | ENHC0014783 |  | Hydrangea | \ | high | 83 |  | 0 | 2024-03-23 |  |  | Pena Traffic Data BI
32705 | User Story | 2024-06-17 10:39 |  | Load historical data | Anthony | Active | ENHC0014783 |  | Poppy | \ | low | 7 |  | 0 | 2024-11-30 |  |  | Load historical data
32780 | User Story | 2024-06-20 13:36 |  | Build tabular model | Anthony | Closed | ENHC0014783 |  | Jasmine | \ | low | 30 |  | 0 | 2024-05-25 |  |  | Build tabular model
33188 | User Story | 2024-07-25 10:42 |  | Deploy to Prod | Anthony | Closed | ENHC0014783 |  | Hydrangea | \ | high | 97 |  | 0 | 2024-03-23 |  |  | Deploy Prod
29038 | Feature | 2023-07-19 18:00 | FCR (fist contact resolution) Service now report and power BI dashboard. |  |  | New | ENHC0014828 | Jake From StateFarm |  | \ | low | 4 |  | 4 |  |  | FCR (fist contact resolution) Service report power BI dashboard.
30022 | Feature | 2023-11-02 09:44 | Service Desk dashboards |  | Steve | Active | ENHC0014930 | Jake From StateFarm | Rose | \ | medium | 49 |  | 2 | 2025-01-04 |  | Service Desk dashboards
32054 | User Story | 2024-04-09 11:34 |  | Modify Service Desk dashboards | Steve | Closed | ENHC0014930 |  | Dahlia | \ | high | 94 |  | 0 | 2024-04-13 |  |  | Modify Service Desk dashboards
33578 | User Story | 2024-08-29 15:18 |  | Fix / enhance Service Desk dashboards | Steve | Active | ENHC0014930 |  | Poppy | \ | low | 10 | 1 | 0 | 2024-11-30 |  |  | Fix / enhance Service Desk dashboards
34220 | User Story | 2024-10-07 11:14 |  | Service Desk cross training | Steve | New | ENHC0014930 |  |  | \ | high | 80 |  | 1 |  |  |  | Service Desk cross training
30600 | Feature | 2023-12-28 11:14 | Pena Crash Data |  |  | On Hold | ENHC0014973 | Lisa Bonet |  | \ | low | 29 |  | 4 |  |  | Pena Crash Data
30795 | Feature | 2024-01-12 08:53 | Shuttle Reports based on data reporting system |  |  | New | ENHC0015005 | Bryan Adams |  | \ | medium | 59 |  | 2 |  |  | Shuttle Reports based data reporting system
31125 | Feature | 2024-01-31 08:02 | Controls project |  |  | On Hold | ENHC0015035 | Larry Wilmore |  | \ | medium | 43 |  | 3 |  |  | Controls project
32308 | User Story | 2024-05-01 13:47 |  | Get requirements / scope | Steve | New | ENHC0015035 |  |  | \ | medium | 59 |  | 0 |  |  |  | Get requirements / scope
31231 | Feature | 2024-02-05 13:52 | DEN Commercial Dashboard 2.0 |  |  | New | ENHC0015044 | Tina Fey |  | \ | high | 88 |  | 4 |  |  | DEN Commercial Dashboard 2.0
31264 | Feature | 2024-02-08 15:48 | Connectors Migration |  |  | New | ENHC0015048 | Rebecca DeMornay |  | \ | medium | 55 |  | 2 |  |  | Connectors Migration
32168 | User Story | 2024-04-17 08:29 |  | Create a list of solutions |  | New | ENHC0015048 |  |  | \ | medium | 49 |  | 0 |  |  |  | Create list solutions
31266 | Feature | 2024-02-09 16:40 | Connect to an external weather dataset for our Snow Dashboards probably via API to help our team better tell the story about runway downtime. |  |  | New | ENHC0015051 | Tracy Chapman |  | \ | low | 32 |  | 2 |  |  | Connect external weather dataset Snow Dashboards probably via API help team better tell story runway downtime.
31483 | Feature | 2024-02-26 14:30 | Update to Maintenance database |  |  | New | ENHC0015069 | Tracy Chapman |  | \ | low | 26 |  | 2 |  |  | Update Maintenance database
31596 | Feature | 2024-03-01 10:11 | New measure for train system |  |  | New | ENHC0014906 | Matthew Broderick |  | \ | medium | 54 |  | 2 |  |  | New measure train system
31603 | Feature | 2024-03-01 12:59 | Comms Center Dashboard |  |  | Active | ENHC0015078 | Tracy Chapman | Anemone | \ | low | 9 |  | 2 | 2025-04-30 |  | Comms Center Dashboard
32436 | User Story | 2024-05-17 13:11 |  | Outbound Phone calls vendor 1 - update dashboard | Harry | Closed | ENHC0015078 |  | Sunflower | \ | medium | 63 |  | 0 | 2024-05-04 |  |  | Outbound Phone calls vendor 1 - update dashboard
32437 | User Story | 2024-05-17 13:17 |  | Phone Calls Vendor 2 - update dashboard | Harry | Active | ENHC0015078 |  | Poppy | \ | low | 8 | 16 | 0 | 2024-11-30 |  |  | Phone Calls Vendor 2 - update dashboard
32438 | User Story | 2024-05-17 13:18 |  | Airport Alarms (update dashboards) | Harry | Closed | ENHC0015078 |  | Hydrangea | \ | high | 79 |  | 0 | 2024-03-23 |  |  | Airport Alarms (update dashboards)
32439 | User Story | 2024-05-17 13:19 |  | Notification System - integration design | Harry | Active | ENHC0015078 |  | Poppy | \ | high | 94 |  | 0 | 2024-11-30 |  |  | Notification System - integration design
32440 | User Story | 2024-05-17 13:22 |  | Notification System - SSIS development |  | New | ENHC0015078 |  | Carnation | \ | high | 68 |  | 0 | 2024-12-15 |  |  | Notification System - SSIS development
32441 | User Story | 2024-05-17 13:22 |  | Notification System - Tabular model development |  | New | ENHC0015078 |  | Carnation | \ | medium | 48 |  | 0 | 2024-12-15 |  |  | Notification System - Tabular model development
32442 | User Story | 2024-05-17 13:22 |  | Notification System - create dashboard |  | New | ENHC0015078 |  | Carnation | \ | medium | 48 |  | 0 | 2024-12-15 |  |  | Notification System - create dashboard
32443 | User Story | 2024-05-17 13:26 |  | Radio calls - update dashboard | Anthony | On Hold | ENHC0015078 |  |  | \ | high | 95 |  | 0 |  |  |  | Radio calls - update dashboard
32444 | User Story | 2024-05-17 13:27 |  | Crisis Management Software Log Book Entries - requirements | Harry | New | ENHC0015078 |  |  | \ | low | 21 |  | 0 |  |  |  | Crisis Management Software Log Book Entries - requirements
32445 | User Story | 2024-05-17 13:29 |  | Crisis Management Software Parking Log Items | Mary | Closed | ENHC0015078 |  | Hydrangea | \ | medium | 41 |  | 0 | 2024-03-23 |  |  | Crisis Management Software Parking Log Items
32446 | User Story | 2024-05-17 13:29 |  | Teams interactions - requirements | Harry | On Hold | ENHC0015078 |  |  | \ | high | 97 |  | 0 |  |  |  | Teams interactions - requirements
33440 | User Story | 2024-08-20 12:01 |  | Single data model - Phone Calls data from Vendor 1 and 2 | Steve | Closed | ENHC0015078 |  | Hydrangea | \ | low | 3 |  | 0 | 2024-03-23 |  |  | Single data model - Phone Calls data Vendor 1 2
31651 | Feature | 2024-03-08 10:20 | OPs Security Screening Occupancy Reporting |  |  | New | ENHC0015091 | Tracy Chapman |  | \ | high | 69 |  | 2 |  |  | OPs Security Screening Occupancy Reporting
31827 | Feature | 2024-03-18 14:41 | Parking - Add Forecasting capability to Parking and Transportation dashboards |  |  | New | ENHC0015102 | Bryan Adams |  | \ | low | 3 |  | 1 |  |  | Parking - Add Forecasting capability Parking Transportation dashboards
31870 | User Story | 2024-03-26 09:10 |  | Add forecasting capability dashboards |  | New | ENHC0015102 |  |  | \ | low | 32 |  | 0 |  |  |  | Add forecasting capability dashboards
33207 | User Story | 2024-07-29 10:40 |  | Gather requirements |  | New | ENHC0015102 |  |  | \ | low | 8 |  | 0 |  |  |  | Gather requirements
31828 | Feature | 2024-03-18 15:06 | Parking - Rideshare 10 or 15 min granular level of detail |  |  | New | ENHC0015103 | Bryan Adams |  | \ | low | 6 |  | 2 |  |  | Parking - Rideshare 10 15 min granular level detail
31871 | User Story | 2024-03-26 09:13 |  | Add the ability to drill down to that level of granularity of detail |  | New | ENHC0015103 |  |  | \ | low | 11 |  | 0 |  |  |  | Add ability drill level granularity detail
31884 | Feature | 2024-03-26 14:14 | Create platform people counter report |  | Anthony | On Hold | ENHC0015114 | Nate Bargatze |  | \ | low | 17 |  | 4 |  |  | Create platform people counter report
31892 | User Story | 2024-03-27 09:41 |  | Create integration for people counter report | Anthony | Closed | ENHC0015114 |  | Sunflower | \ | medium | 62 |  | 0 | 2024-05-04 |  |  | Create integration people counter report
32620 | User Story | 2024-06-06 13:45 |  | Create tabular model for people counter | Mary | Closed | ENHC0015114 |  | Jasmine | \ | medium | 43 |  | 0 | 2024-05-25 |  |  | Create tabular model people counter
32837 | User Story | 2024-06-27 10:43 |  | Create dashboard for people counters | Mary | Closed | ENHC0015114 |  | Jasmine | \ | high | 82 |  | 0 | 2024-05-25 |  |  | Create dashboard people counters
32064 | Feature | 2024-04-10 10:44 | Procurement Opportunities to Flydenver API Gateway |  |  | Active | ENHC0015126 | Michelle Obama | Lily | \ | low | 24 |  | 4 | 2025-01-25 |  | Procurement Opportunities Flydenver API Gateway
32314 | User Story | 2024-05-01 15:10 |  | Architecture | Rachel | Closed | ENHC0015126 |  | Zinnia | \ | low | 19 |  | 0 | 2024-06-15 |  |  | Architecture
34117 | User Story | 2024-09-30 13:42 |  | SSIS integration from Sharepoint to data gateway | Anthony | Closed | ENHC0015126 |  | Zinnia | \ | low | 16 | 20 | 0 | 2024-06-15 |  |  | SSIS integration Sharepoint data gateway
34459 | User Story | 2024-10-23 13:17 |  | Deploy Data Gateway | Anthony | On Hold | ENHC0015126 |  | Poppy | \ | high | 70 |  | 0 | 2024-11-30 |  |  | Deploy Data Gateway
32323 | Feature | 2024-05-03 08:24 | Update SSRS Business Directory Report to be ADA Complaint. |  |  | On Hold | ENHC0015165 | Michelle Obama |  | \ | high | 85 |  | 2 |  |  | Update SSRS Business Directory Report ADA Complaint.
32419 | User Story | 2024-05-14 13:01 |  | Update report | Anthony | Deployment | ENHC0015165 |  |  | \ | medium | 55 |  | 0 |  |  |  | Update report
32363 | Feature | 2024-05-08 10:08 | Parking - Lost and Found Dashboard |  |  | New | ENHC0015170 | Mark Cuban |  | \ | high | 70 |  | 1 |  |  | Parking - Lost Found Dashboard
32364 | Feature | 2024-05-08 11:51 | Capture concessionaire transaction data in the concessions warehouse. |  |  | Active | ENHC0015171 | Branden Flowers | Snapdragon | \ | medium | 60 |  | 3 | 2025-03-08 |  | Capture concessionaire transaction data concessions warehouse.
32582 | User Story | 2024-06-05 11:52 |  | Load transactions and connect to API | Mary | Closed | ENHC0015171 |  | Lavender | \ | medium | 55 |  | 0 | 2024-07-27 |  |  | Load transactions connect API
34166 | User Story | 2024-10-02 13:27 |  | Concession - Transactions Count Demo & UAT | Mary | Active | ENHC0015171 |  | Poppy | \ | low | 4 |  | 0 | 2024-11-30 |  |  | Concession - Transactions Count Demo & UAT
32519 | Feature | 2024-05-23 11:29 | Baggage Handling System data into the DEN Data Warehouse |  |  | On Hold | ENHC0015191 | Matthew Broderick |  | \ | high | 85 |  | 3 |  |  | Baggage Handling System data DEN Data Warehouse
32552 | User Story | 2024-05-31 12:39 |  | Test connectivity to LogPlan Server | Anthony | Closed | ENHC0015191 |  | Daffodil | \ | high | 91 |  | 0 | 2024-07-06 |  |  | Test connectivity LogPlan Server
32670 | User Story | 2024-06-12 09:52 |  | Extract, transform and load data | Anthony | Awaiting Customer | ENHC0015191 |  |  | \ | high | 84 |  | 0 |  |  |  | Extract, transform load data
32531 | Feature | 2024-05-29 08:37 | Expanding the data that is being passed to us from People counter source via API |  | Steve | Active | ENHC0015195 | Tracy Chapman | Bluebell | \ | low | 25 |  | 1 | 2025-03-29 |  | Expanding data passed us People counter source via API
32631 | User Story | 2024-06-10 14:50 |  | Rob to look at the data integration API |  | Closed | ENHC0015195 |  | Jasmine | \ | high | 87 |  | 0 | 2024-05-25 |  |  | Rob look data integration API
33275 | User Story | 2024-08-05 10:10 |  | Gathering requirements | Steve | Closed | ENHC0015195 |  | Lavender | \ | medium | 43 | 4 | 0 | 2024-07-27 |  |  | Gathering requirements
34517 | User Story | 2024-10-24 12:34 |  | Expand people counter data | Steve | Closed | ENHC0015195 |  | Poppy | \ | low | 5 | 5 | 0 | 2024-11-30 |  |  | Expand people counter data
34653 | User Story | 2024-11-06 10:11 |  | Develop SSIS integration | Steve | Active | ENHC0015195 |  | Poppy | \ | low | 10 |  | 0 | 2024-11-30 |  |  | Develop SSIS integration
32669 | Feature | 2024-06-12 09:42 | Request Reports on People counter data |  |  | New | ENHC0015215 | Robert Downey |  | \ | high | 72 |  | 0 |  |  | Request Reports People counter data
32907 | Feature | 2024-07-03 09:30 | Concessions gross sales report - ADA compliant |  |  | On Hold | ENHC0015247 | Lawrence Taylor |  | \ | medium | 41 |  | 0 |  |  | Concessions gross sales report - ADA compliant
33011 | Feature | 2024-07-15 11:27 | Update Airline stats SSRS report to be ADA Compliant. |  |  | On Hold | ENHC0015257 | George Clooney |  | \ | low | 19 |  | 0 |  |  | Update Airline stats SSRS report ADA Compliant.
33125 | User Story | 2024-07-22 10:32 |  | Create SSRS report for ADA Compliant | Harry | On Hold | ENHC0015257 |  |  | \ | high | 70 |  | 0 |  |  |  | Create SSRS report ADA Compliant
33013 | Feature | 2024-07-16 09:55 | Add Search for the Fuel form and process |  |  | New | ENHC0015258 | Steve Martin |  | \ | low | 24 |  | 2 |  |  | Add Search Fuel form process
34168 | User Story | 2024-10-02 14:10 |  | Gather Fuel requirements | Rachel | New | ENHC0015258 |  | Poppy | \ | low | 2 | 0 | 0 | 2024-11-30 |  |  | Gather Fuel requirements
33034 | Feature | 2024-07-16 11:33 | Non-Production Network Production/Inventory Values and Cost Estimation sheets need adjusting/correcting (use attached docs) |  |  | New | ENHC0015259 | Travis Barker |  | \ | high | 84 |  | 1 |  |  | Non-Production Network Production/Inventory Values Cost Estimation sheets need adjusting/correcting (use attached docs)
33335 | Feature | 2024-08-09 17:38 | Add procurement data to data warehouse |  |  | On Hold | ENHC0015288 | Eliot Page |  | \ | high | 81 |  | 4 |  |  | Add procurement data data warehouse
34219 | User Story | 2024-10-07 10:41 |  | Provide advice to Procurement software | Steve | Closed | ENHC0015288 |  | Zinnia | \ | low | 2 |  | 0 | 2024-06-15 |  |  | Provide advice Procurement software
33367 | Feature | 2024-08-13 16:05 | Parking Data coming online from Contractor |  | Anthony | Active | ENHC0015292 | Bryan Adams | Lily | \ | medium | 52 |  | 2 | 2025-01-25 |  | Parking Data coming online Contractor
33445 | User Story | 2024-08-20 15:16 |  | Research vendor docs and API requirements | Anthony | Closed | ENHC0015292 |  | Hydrangea | \ | medium | 38 |  | 0 | 2024-03-23 |  |  | Research vendor docs API requirements
33899 | User Story | 2024-09-20 09:52 |  | Map parking data file to existing parking table. | Anthony | Closed | ENHC0015292 |  | Lavender | \ | medium | 58 | 4 | 0 | 2024-07-27 |  |  | Map parking data file existing parking table.
33967 | User Story | 2024-09-24 14:44 |  | Parking - Update SSIS Integration for Daily Transaction Data. | Anthony | Active | ENHC0015292 |  | Poppy | \ | low | 30 | 10 | 0 | 2024-11-30 |  |  | Parking - Update SSIS Integration Daily Transaction Data.
33968 | User Story | 2024-09-24 14:46 |  | Develop SSIS integration for Occupancy Data - Near Realtime. | Anthony | New | ENHC0015292 |  |  | \ | low | 14 |  | 0 |  |  |  | Develop SSIS integration Occupancy Data - Near Realtime.
33969 | User Story | 2024-09-24 14:47 |  | Update Tabular Model for Transaction Data. | Anthony | New | ENHC0015292 |  |  | \ | high | 80 |  | 0 |  |  |  | Update Tabular Model Transaction Data.
33706 | Feature | 2024-09-09 11:24 | Crisis Management Workflow API Call Proof of Concept/Documentation |  |  | On Hold | ENHC0015314 | Michael Myers | Lavender | \ | high | 95 |  | 1 |  |  | Crisis Management Workflow API Call Proof Concept/Documentation
34114 | User Story | 2024-09-30 10:35 |  | Workflow data Integration from Crisis Management Software Workflow | Mary | On Hold | ENHC0015314 |  |  | \ | medium | 40 | 10 | 0 |  |  |  | Workflow data Integration Crisis Management Software Workflow
33880 | Feature | 2024-09-19 10:03 | Updates to Concession Incentive Program |  |  | New | ENHC0015326 | Lawrence Taylor |  | \ | high | 77 |  | 3 |  |  | Updates Concession Incentive Program
33897 | Feature | 2024-09-20 08:50 | Review and update DW due to 'decustomizing' Maintnance source fields / Maintenance source reimplementation |  | Rachel | Active | ENHC0015327 | Michael Douglas | Bluebell | \ | low | 24 |  | 2 | 2025-03-29 |  | Review update DW due 'decustomizing' Maintnance source fields / Maintenance source reimplementation
34406 | User Story | 2024-10-18 11:00 |  | Maintenance source - Review technical document | Mary | Closed | ENHC0015327 |  | Poppy | \ | high | 85 |  | 0 | 2024-11-30 |  |  | Maintenance source - Review technical document
34589 | User Story | 2024-10-31 10:08 |  | Maven Sprint 2 development | Mary | Active | ENHC0015327 |  | Poppy | \ | high | 160 | 16 | 0 | 2024-11-30 |  |  | Maven Sprint 2 development
33977 | Feature | 2024-09-24 16:04 | Create new data fields in Maintenance Data warehouse |  |  | New | ENHC0015351 | Eliot Page |  | \ | high | 80 |  | 0 |  |  | Create new data fields Maintenance Data warehouse
34314 | Feature | 2024-10-10 13:40 | Add concourse to Flight Schedule Analytical tabular model |  |  | New | ENHC0015381 | Tracy Chapman |  | \ | low | 7 |  | 3 |  |  | Add concourse Flight Schedule Analytical tabular model
34334 | Feature | 2024-10-14 13:37 | PowerBI query from Finance Source |  |  | New | ENHC0015409 | Lawrence Taylor |  | \ | low | 23 |  | 2 |  |  | PowerBI query Finance Source
34347 | Feature | 2024-10-15 10:38 | Add a field to the Employee Extract file in the Database |  |  | New | ENHC0015410 | Renee Zellwegger |  | \ | medium | 58 |  | 4 |  |  | Add field Employee Extract file Database
34372 | Feature | 2024-10-15 13:53 | We need all of the Snow data from Crisis Management source moved into the Data Warehouse |  | Mary | Active | ENHC0015413 | Tracy Chapman | Snapdragon | \ | low | 14 |  | 2 | 2025-03-08 |  | need Snow data Crisis Management source moved Data Warehouse
34463 | User Story | 2024-10-23 13:29 |  | Crisis Management Source- Snow requirements gathering | Mary | New | ENHC0015413 |  | Poppy | \ | high | 67 |  | 0 | 2024-11-30 |  |  | Crisis Management Source- Snow requirements gathering
34410 | Feature | 2024-10-18 12:46 | Snow Deactivation data model from source to Power BI for DEN Snow Dashboard |  |  | New | ENHC0015418 | Derek Henry |  | \ | high | 98 |  | 4 |  |  | Snow Deactivation data model source Power BI DEN Snow Dashboard
34433 | Feature | 2024-10-21 14:31 | Pull regulation data submissions into database so GIS team can access the data |  |  | New | ENHC0015425 | Chelesa Clinton |  | \ | low | 29 |  | 3 |  |  | Pull regulation data submissions database GIS team access data
34434 | Feature | 2024-10-21 17:21 | Biometric Exit dashboard request |  |  | New | ENHC0015426 | Eliot Page |  | \ | high | 75 |  | 3 |  |  | Biometric Exit dashboard request
34436 | Feature | 2024-10-22 09:54 | In the Service Request Data Warehouse, need the "SENT TO" field created |  |  | New | ENHC0015428 | Matthew Broderick |  | \ | low | 5 |  | 2 |  |  | Service Request Data Warehouse, need "SENT TO" field created
34457 | Feature | 2024-10-23 11:59 | Airport ops data extract to DEN BI data warehouse |  | Anthony | Active | ENHC0015432 | Robert Downey | Marigold | \ | low | 33 |  | 1 | 2025-02-15 |  | Airport ops data extract DEN BI data warehouse
34464 | User Story | 2024-10-23 13:31 |  | Airport Ops - Research existing FIDS reports and requirements | Anthony | Active | ENHC0015432 |  | Poppy | \ | low | 4 | 2 | 0 | 2024-11-30 |  |  | Airport Ops - Research existing FIDS reports requirements
34568 | Feature | 2024-10-30 11:30 | CNG Crisis Management report |  | Mary | Active | ENHC0015443 | Bryan Adams | Marigold | \ | high | 93 |  | 4 | 2025-02-15 |  | CNG Crisis Management report
34586 | Feature | 2024-10-31 08:06 | Load Screening Q3 data |  | Steve | Active | ENHC0015449 | James Murray | Poppy | \ | medium | 63 |  | 0 | 2024-11-30 |  | Load Screening Q3 data
34587 | Feature | 2024-10-31 08:09 | Insurance data to Power BI |  | Steve | Active | ENHC0015450 | Derek Henry | Poppy | \ | medium | 59 |  | 4 | 2024-11-30 |  | Insurance data Power BI
34588 | Feature | 2024-10-31 08:10 | Products data cleanup |  | Steve | Active | ENHC0015451 | Lonnie Anderson | Poppy | \ | high | 91 |  | 1 | 2024-11-30 |  | Products data cleanup
28052 | Feature | 2023-03-22 12:12 | Sustainability Dashboards |  | Mary | Closed | ENHC0014124 | James Murray | Zinnia | \ | low | 18 |  | 2 | 2024-06-15 |  | Sustainability Dashboards
26601 | User Story | 2022-07-01 15:15 |  | Greenhouse Gas Emissions Dashboard | Mary | Closed | ENHC0014124 |  | Chrysanthemum | \ | low | 2 |  | 2 | 2024-08-17 |  |  | Greenhouse Gas Emissions Dashboard
26603 | User Story | 2022-07-01 15:17 |  | Energy Sustainability Dashboard | Mary | Closed | ENHC0014126 |  | Orchid | \ | low | 19 |  | 2 | 2024-10-19 |  |  | Energy Sustainability Dashboard
30707 | User Story | 2024-01-04 09:29 |  | Compost and Trash Data Integration | Mary | Closed | ENHC0014124 |  | Hibiscus | \ | medium | 52 |  | 0 | 2024-09-07 |  |  | Compost Trash Data Integration
30712 | User Story | 2024-01-04 09:51 |  | User training on the Greenhouse dashboard | Mary | Closed | ENHC0014124 |  | Hibiscus | \ | medium | 49 |  | 0 | 2024-09-07 |  |  | User training Greenhouse dashboard
30796 | User Story | 2024-01-12 10:32 |  | Jet Fuel Data | Mary | Closed | ENHC0014124 |  | Gardenia | \ | high | 79 |  | 0 | 2024-09-28 |  |  | Jet Fuel Data
30797 | User Story | 2024-01-12 10:32 |  | Propane Gas Data | Mary | Closed | ENHC0014124 |  | Gardenia | \ | high | 85 |  | 0 | 2024-09-28 |  |  | Propane Gas Data
31041 | User Story | 2024-01-25 10:11 |  | Update Energy dashboards to remove Inforiver formatting | Mary | Closed | ENHC0014124 |  | Orchid | \ | low | 21 |  | 0 | 2024-10-19 |  |  | Update Energy dashboards remove Inforiver formatting
31241 | User Story | 2024-02-06 11:06 |  | Combine all fuel sources into one dashboard | Mary | Closed | ENHC0014124 |  | Gardenia | \ | medium | 43 |  | 0 | 2024-09-28 |  |  | Combine fuel sources one dashboard
31893 | User Story | 2024-03-27 10:27 |  | Build Emission Dashboard | Mary | Closed | ENHC0014124 |  | Orchid | \ | medium | 42 |  | 0 | 2024-10-19 |  |  | Build Emission Dashboard
28806 | Feature | 2023-06-12 10:59 | Upgrade to latest version - Connector 1 |  | Steve | Closed | ENHC0014775 | Rebecca DeMornay | Jasmine | \ | low | 6 |  | 2 | 2024-05-25 |  | Upgrade latest version - Connector 1
29299 | User Story | 2023-08-10 14:38 |  | Development | Steve | Closed | ENHC0014775 |  | Jasmine | \ | low | 1 |  | 0 | 2024-05-25 |  |  | Development
29793 | Feature | 2023-10-05 17:15 | Power BI dashboard for Network devices age |  |  | Closed | ENHC0014909 | Michael Keaton | Lavender | \ | high | 78 |  | 2 | 2024-07-27 |  | Power BI dashboard Network devices age
30097 | User Story | 2023-11-13 10:43 |  | Scoping - Power BI dashboard for Network devices age | Mel | Closed | ENHC0014909 |  | Hibiscus | \ | low | 27 |  | 0 | 2024-09-07 |  |  | Scoping - Power BI dashboard Network devices age
30789 | User Story | 2024-01-11 12:05 |  | Network Device Age - Build Dashboard | Mary | Closed | ENHC0014909 |  | Dahlia | \ | high | 71 |  | 0 | 2024-04-13 |  |  | Network Device Age - Build Dashboard
29816 | Feature | 2023-10-09 09:08 | Updates to concessions gross sales |  | Anthony | Closed | ENHC0014911 | Lawrence Taylor | Jasmine | \ | medium | 42 |  | 2 | 2024-05-25 |  | Updates concessions gross sales
30986 | User Story | 2024-01-23 12:44 |  | Updates to concessions gross sales | Anthony | Closed | ENHC0014911 |  | Hydrangea | \ | low | 15 |  | 0 | 2024-03-23 |  |  | Updates concessions gross sales
32541 | User Story | 2024-05-29 13:07 |  | Deploy to PROD | Anthony | Closed | ENHC0014911 |  | Lavender | \ | low | 19 |  | 0 | 2024-07-27 |  |  | Deploy PROD
31710 | Feature | 2024-03-12 23:01 | ADA Monthly Service Reports Automation |  |  | Closed | ENHC0015094 | Renee Zellwegger | Orchid | \ | low | 31 |  | 3 | 2024-10-19 |  | ADA Monthly Service Reports Automation
32688 | User Story | 2024-06-13 08:10 |  | Research / Gather Requirements | Harry | Closed | ENHC0015094 |  | Lavender | \ | high | 79 |  | 0 | 2024-07-27 |  |  | Research / Gather Requirements
33996 | User Story | 2024-09-26 10:38 |  | Development - ADA Vendor 1 Automation | Harry | Closed | ENHC0015094 |  | Zinnia | \ | low | 5 | 5 | 0 | 2024-06-15 |  |  | Development - ADA Vendor 1 Automation
34103 | User Story | 2024-09-30 08:57 |  | Development - ADA Vendor 2 Automation | Harry | Closed | ENHC0015094 |  | Zinnia | \ | low | 10 | 10 | 0 | 2024-06-15 |  |  | Development - ADA Vendor 2 Automation
34104 | User Story | 2024-09-30 08:57 |  | Development - ADA Kiosks Automation | Harry | Closed | ENHC0015094 |  | Zinnia | \ | low | 20 | 25 | 0 | 2024-06-15 |  |  | Development - ADA Kiosks Automation
34105 | User Story | 2024-09-30 08:58 |  | Development - ADA Vendor 3 Automation | Harry | Closed | ENHC0015094 |  | Zinnia | \ | low | 20 | 15 | 0 | 2024-06-15 |  |  | Development - ADA Vendor 3 Automation
32321 | Feature | 2024-05-02 13:23 | We need to pull data from the parking vendor into the data warehouse to enable regular reporting on Parking Lot Capacity |  |  | Closed | ENHC0015163 | Tracy Chapman | Tulip | \ | low | 2 |  | 0 | 2024-11-09 |  | need pull data parking vendor data warehouse enable regular reporting Parking Lot Capacity
32413 | User Story | 2024-05-14 09:58 |  | Research data | Anthony | Closed | ENHC0015163 |  | Tulip | \ | low | 1 |  | 0 | 2024-11-09 |  |  | Research data
32540 | User Story | 2024-05-29 12:50 |  | Pull data into the warehouse | Mary | Closed | ENHC0015163 |  | Dahlia | \ | low | 5 |  | 0 | 2024-04-13 |  |  | Pull data warehouse
32702 | User Story | 2024-06-17 10:33 |  | UAT - Parking stats | Mary | Closed | ENHC0015163 |  | Daffodil | \ | medium | 56 |  | 0 | 2024-07-06 |  |  | UAT - Parking stats
32813 | User Story | 2024-06-25 13:41 |  | Production Deployment - Parking Stats | Mary | Closed | ENHC0015163 |  | Daffodil | \ | high | 68 |  | 0 | 2024-07-06 |  |  | Production Deployment - Parking Stats
32338 | Feature | 2024-05-07 08:46 | Self Bagdrop Dashboard Enhancement |  |  | Closed | ENHC0015169 | Nate Bargatze | Daffodil | \ | high | 72 |  | 1 | 2024-07-06 |  | Self Bagdrop Dashboard Enhancement
32358 | User Story | 2024-05-07 14:39 |  | Add additional dashboards | Mary | Closed | ENHC0015169 |  | Tulip | \ | medium | 48 |  | 0 | 2024-11-09 |  |  | Add additional dashboards
32416 | Feature | 2024-05-14 11:47 | Maintenance software rehosting testing |  |  | Closed | ENHC0015179 | Russell Peters | Poppy | \ | medium | 37 |  | 0 | 2024-11-30 |  | Maintenance software rehosting testing
32417 | User Story | 2024-05-14 11:49 |  | Maintenance Software connectivity testing | Steve | Closed | ENHC0015179 |  | Dahlia | \ | high | 83 |  | 0 | 2024-04-13 |  |  | Maintenance Software connectivity testing
32536 | Feature | 2024-05-29 10:11 | Add Previous Week Page Report to OPS Ramp Tower Metrics |  |  | Closed | ENHC0015196 | Renee Zellwegger | Hibiscus | \ | medium | 45 |  | 0 | 2024-09-07 |  | Add Previous Week Page Report OPS Ramp Tower Metrics
32537 | Feature | 2024-05-29 10:13 | OPS On Time Performance Report |  |  | Closed | ENHC0015197 | Lawrence Taylor | Jasmine | \ | low | 32 |  | 4 | 2024-05-25 |  | OPS Time Performance Report
32538 | Feature | 2024-05-29 10:15 | OPS TSA Checkpoint Wait Times |  |  | Closed | ENHC0015198 | Michael Douglas | Jasmine | \ | low | 10 |  | 1 | 2024-05-25 |  | OPS TSA Checkpoint Wait Times
32691 | Feature | 2024-06-13 12:01 | Microsoft Fabric POC |  |  | Closed | ENHC0015218 | Chris Martin | Tulip | \ | low | 6 |  | 0 | 2024-11-09 |  | Microsoft Fabric POC
33446 | User Story | 2024-08-20 15:18 |  | Complete Tutorials | Steve | Closed | ENHC0015218 |  | Hydrangea | \ | low | 9 |  | 0 | 2024-03-23 |  |  | Complete Tutorials
33447 | User Story | 2024-08-20 15:18 |  | Complete Tutorials | Anthony | Closed | ENHC0015218 |  | Hydrangea | \ | high | 67 |  | 0 | 2024-03-23 |  |  | Complete Tutorials
33448 | User Story | 2024-08-20 15:18 |  | Complete Tutorials | Mary | Closed | ENHC0015218 |  | Hydrangea | \ | high | 67 |  | 0 | 2024-03-23 |  |  | Complete Tutorials
33449 | User Story | 2024-08-20 15:20 |  | Complete Tutorials | Harry | Closed | ENHC0015218 |  | Hydrangea | \ | low | 24 |  | 0 | 2024-03-23 |  |  | Complete Tutorials
33683 | User Story | 2024-09-06 09:40 |  | ML workshop |  | Closed | ENHC0015218 |  | Lavender | \ | medium | 63 |  | 0 | 2024-07-27 |  |  | ML workshop
33684 | User Story | 2024-09-06 09:40 |  | GenAI workshop |  | Closed | ENHC0015218 |  | Lavender | \ | low | 7 |  | 0 | 2024-07-27 |  |  | GenAI workshop
32692 | Feature | 2024-06-13 12:07 | Microsoft Purview POC - Data Quality |  |  | Closed | ENHC0015220 | Chris Martin | Dahlia | \ | high | 86 |  | 1 | 2024-04-13 |  | Microsoft Purview POC - Data Quality
33329 | User Story | 2024-08-09 11:49 |  | Microsoft Purview POC - Data Quality | Rachel | Closed | ENHC0015220 |  | Hydrangea | \ | low | 11 |  | 0 | 2024-03-23 |  |  | Microsoft Purview POC - Data Quality
32964 | Feature | 2024-07-09 10:38 | AskIT/ServiceNow fields imported into the Data Warehouse. |  |  | Closed | ENHC0015249 | Renee Zellwegger | Dahlia | \ | low | 17 |  | 1 | 2024-04-13 |  | AskIT/ServiceNow fields imported Data Warehouse.
33012 | User Story | 2024-07-15 11:52 |  | Research | Mary | Closed | ENHC0015249 |  | Jasmine | \ | medium | 46 |  | 0 | 2024-05-25 |  |  | Research
33218 | Feature | 2024-07-31 11:56 | BI reports from Finance source for cash posting |  |  | Closed | ENHC0015273 | Michael Douglas | Hibiscus | \ | high | 77 |  | 3 | 2024-09-07 |  | BI reports Finance source cash posting
33330 | User Story | 2024-08-09 11:52 |  | Cash Posting Finance source | Steve | Closed | ENHC0015273 |  | Hydrangea | \ | high | 84 |  | 0 | 2024-03-23 |  |  | Cash Posting Finance source
34315 | Feature | 2024-10-10 13:56 | Maintenance Division data collection and analysis for Q3/V.100 |  |  | Closed | ENHC0015382 | Bryan Adams | Orchid | \ | low | 21 |  | 1 | 2024-10-19 |  | Maintenance Division data collection analysis Q3/V.100
34316 | Feature | 2024-10-10 14:02 | Maintenance Division data analytics for Q3/Vision100 |  |  | Closed | ENHC0015387 | Eliot Page | Sunflower | \ | low | 8 |  | 3 | 2024-05-04 |  | Maintenance Division data analytics Q3/Vision100