## Sheet1
ID | Work Item Type | Created Date | Feature Title | User Story Title | Assigned To | State | AskIT Enhancement Number | Customer Name | Iteration Path | Area Path | Level of Effort | Story Points (0 - 99) | Value (0 - 99) | Priority (0 - 4) | Target Date | Business Value (0 - 999)
17021 | Feature | 2019-07-01 09:44 | Add UMD for "full de-ice event" dates into flight model |  |  | New | ENHC0010862 | Matthew Broderick | \ | \ | Medium |  |  | 2
27621 | Feature | 2023-02-02 09:49 | Compensation rates are not populating in Concessions reports. |  | Anthony | Active | ENHC0014455 | Branden Flowers | \ | \ |  |  |  | 2
30708 | User Story | 2024-01-04 09:29 |  | Finance Source - Develop to pull compensation rates | Anthony | On Hold | ENHC0014455 |  | \Poppy | \ |  | 20 |  | 0
28848 | Feature | 2023-06-20 11:49 | Migrate Pena traffic data from source to prod |  | Anthony | On Hold | ENHC0014783 | Chelesa Clinton | \ | \ | Medium
32169 | User Story | 2024-04-17 08:31 |  | Pena Traffic Data in BI | Anthony | Closed | ENHC0014783 |  | \Hydrangea | \ |  |  |  | 0
32705 | User Story | 2024-06-17 10:39 |  | Load historical data | Anthony | Active | ENHC0014783 |  | \Poppy | \ |  |  |  | 0
32780 | User Story | 2024-06-20 13:36 |  | Build tabular model | Anthony | Closed | ENHC0014783 |  | \ | \ |  |  |  | 0
33188 | User Story | 2024-07-25 10:42 |  | Deploy to Prod | Anthony | Closed | ENHC0014783 |  | \Hydrangea | \ |  |  |  | 0
29038 | Feature | 2023-07-19 18:00 | FCR (fist contact resolution) Service now report and power BI dashboard. |  |  | New | ENHC0014828 | Jake From StateFarm | \ | \ |  |  |  | 4
30022 | Feature | 2023-11-02 09:44 | Service Desk dashboards |  | Steve | Active | ENHC0014930 | Jake From StateFarm | \ | \ | High |  |  | 2 | 2024-05-12 18:00
32054 | User Story | 2024-04-09 11:34 |  | Modify Service Desk dashboards | Steve | Closed | ENHC0014930 |  | \Dahlia | \ |  |  |  | 0
33578 | User Story | 2024-08-29 15:18 |  | Fix / enhance Service Desk dashboards | Steve | Active | ENHC0014930 |  | \Poppy | \ |  | 10 | 1 | 0
34220 | User Story | 2024-10-07 11:14 |  | Service Desk cross training | Steve | New | ENHC0014930 |  | \ | \ |  |  |  | 1
30600 | Feature | 2023-12-28 11:14 | Pena Crash Data |  |  | On Hold | ENHC0014973 | Lisa Bonet | \ | \ |  |  |  | 4
30795 | Feature | 2024-01-12 08:53 | Shuttle Reports based on data reporting system |  |  | New | ENHC0015005 | Bryan Adams | \ | \
31125 | Feature | 2024-01-31 08:02 | Controls project |  |  | On Hold | ENHC0015035 | Larry Wilmore | \ | \
32308 | User Story | 2024-05-01 13:47 |  | Get requirements / scope | Steve | New | ENHC0015035 |  | \ | \ |  |  |  | 0
31231 | Feature | 2024-02-05 13:52 | DEN Commercial Dashboard 2.0 |  |  | New | ENHC0015044 | Tina Fey | \ | \
31264 | Feature | 2024-02-08 15:48 | Connectors Migration |  |  | New | ENHC0015048 | Rebecca DeMornay | \ | \
32168 | User Story | 2024-04-17 08:29 |  | Create a list of solutions |  | New | ENHC0015048 |  | \ | \ |  |  |  | 0
31266 | Feature | 2024-02-09 16:40 | Connect to an external weather dataset for our Snow Dashboards probably via API to help our team better tell the story about runway downtime. |  |  | New | ENHC0015051 | Tracy Chapman | \ | \ |  |  |  | 2
31483 | Feature | 2024-02-26 14:30 | Update to Maintenance database |  |  | New | ENHC0015069 | Tracy Chapman | \ | \
31596 | Feature | 2024-03-01 10:11 | New measure for train system |  |  | New | ENHC0014906 | Matthew Broderick | \ | \
31603 | Feature | 2024-03-01 12:59 | Comms Center Dashboard |  |  | Active | ENHC0015078 | Tracy Chapman | \ | \
32436 | User Story | 2024-05-17 13:11 |  | Outbound Phone calls vendor 1 - update dashboard | Harry | Closed | ENHC0015078 |  | \Sunflower | \ |  |  |  | 0
32437 | User Story | 2024-05-17 13:17 |  | Phone Calls Vendor 2 - update dashboard | Harry | Active | ENHC0015078 |  | \Poppy | \ |  | 8 | 16 | 0
32438 | User Story | 2024-05-17 13:18 |  | Airport Alarms (update dashboards) | Harry | Closed | ENHC0015078 |  | \Hydrangea | \ |  |  |  | 0
32439 | User Story | 2024-05-17 13:19 |  | Notification System - integration design | Harry | Active | ENHC0015078 |  | \Poppy | \ |  |  |  | 0
32440 | User Story | 2024-05-17 13:22 |  | Notification System - SSIS development |  | New | ENHC0015078 |  | \Carnation | \ |  |  |  | 0
32441 | User Story | 2024-05-17 13:22 |  | Notification System - Tabular model development |  | New | ENHC0015078 |  | \Carnation | \ |  |  |  | 0
32442 | User Story | 2024-05-17 13:22 |  | Notification System - create dashboard |  | New | ENHC0015078 |  | \Carnation | \ |  |  |  | 0
32443 | User Story | 2024-05-17 13:26 |  | Radio calls - update dashboard | Anthony | On Hold | ENHC0015078 |  | \ | \ |  |  |  | 0
32444 | User Story | 2024-05-17 13:27 |  | Crisis Management Software Log Book Entries - requirements | Harry | New | ENHC0015078 |  | \ | \ |  |  |  | 0
32445 | User Story | 2024-05-17 13:29 |  | Crisis Management Software Parking Log Items | Mary | Closed | ENHC0015078 |  | \Hydrangea | \ |  |  |  | 0
32446 | User Story | 2024-05-17 13:29 |  | Teams interactions - requirements | Harry | On Hold | ENHC0015078 |  | \ | \ |  |  |  | 0
33440 | User Story | 2024-08-20 12:01 |  | Single data model - Phone Calls data from Vendor 1 and 2 | Steve | Closed | ENHC0015078 |  | \Hydrangea | \ |  |  |  | 0
31651 | Feature | 2024-03-08 10:20 | OPs Security Screening Occupancy Reporting |  |  | New | ENHC0015091 | Tracy Chapman | \ | \
31827 | Feature | 2024-03-18 14:41 | Parking - Add Forecasting capability to Parking and Transportation dashboards |  |  | New | ENHC0015102 | Bryan Adams | \ | \
31870 | User Story | 2024-03-26 09:10 |  | Add forecasting capability dashboards |  | New | ENHC0015102 |  | \ | \ |  |  |  | 0
33207 | User Story | 2024-07-29 10:40 |  | Gather requirements |  | New | ENHC0015102 |  | \ | \ |  |  |  | 0
31828 | Feature | 2024-03-18 15:06 | Parking - Rideshare 10 or 15 min granular level of detail |  |  | New | ENHC0015103 | Bryan Adams | \ | \
31871 | User Story | 2024-03-26 09:13 |  | Add the ability to drill down to that level of granularity of detail |  | New | ENHC0015103 |  | \ | \ |  |  |  | 0
31884 | Feature | 2024-03-26 14:14 | Create platform people counter report |  | Anthony | On Hold | ENHC0015114 | Nate Bargatze | \ | \
31892 | User Story | 2024-03-27 09:41 |  | Create integration for people counter report | Anthony | Closed | ENHC0015114 |  | \Sunflower | \ |  |  |  | 0
32620 | User Story | 2024-06-06 13:45 |  | Create tabular model for people counter | Mary | Closed | ENHC0015114 |  | \Jasmine | \ |  |  |  | 0
32837 | User Story | 2024-06-27 10:43 |  | Create dashboard for people counters | Mary | Closed | ENHC0015114 |  | \Jasmine | \ |  |  |  | 0
32064 | Feature | 2024-04-10 10:44 | Procurement Opportunities to Flydenver API Gateway |  |  | Active | ENHC0015126 | Michelle Obama | \ | \
32314 | User Story | 2024-05-01 15:10 |  | Architecture | Rachel | Closed | ENHC0015126 |  | \Zinnia | \ |  |  |  | 0
34117 | User Story | 2024-09-30 13:42 |  | SSIS integration from Sharepoint to data gateway | Anthony | Closed | ENHC0015126 |  | \Zinnia | \ |  | 16 | 20 | 0
34459 | User Story | 2024-10-23 13:17 |  | Deploy Data Gateway | Anthony | On Hold | ENHC0015126 |  | \Poppy | \ |  |  |  | 0
32323 | Feature | 2024-05-03 08:24 | Update SSRS Business Directory Report to be ADA Complaint. |  |  | On Hold | ENHC0015165 | Michelle Obama | \ | \ |  |  |  | 2
32419 | User Story | 2024-05-14 13:01 |  | Update report | Anthony | Deployment | ENHC0015165 |  | \ | \ |  |  |  | 0
32363 | Feature | 2024-05-08 10:08 | Parking - Lost and Found Dashboard |  |  | New | ENHC0015170 | Mark Cuban | \ | \
32364 | Feature | 2024-05-08 11:51 | Capture concessionaire transaction data in the concessions warehouse. |  |  | Active | ENHC0015171 | Branden Flowers | \ | \
32582 | User Story | 2024-06-05 11:52 |  | Load transactions and connect to API | Mary | Closed | ENHC0015171 |  | \Lavender | \ |  |  |  | 0
34166 | User Story | 2024-10-02 13:27 |  | Concession - Transactions Count Demo & UAT | Mary | Active | ENHC0015171 |  | \Poppy | \ |  | 4 |  | 0
32519 | Feature | 2024-05-23 11:29 | Baggage Handling System data into the DEN Data Warehouse |  |  | On Hold | ENHC0015191 | Matthew Broderick | \ | \
32552 | User Story | 2024-05-31 12:39 |  | Test connectivity to LogPlan Server | Anthony | Closed | ENHC0015191 |  | \Daffodil | \ |  |  |  | 0
32670 | User Story | 2024-06-12 09:52 |  | Extract, transform and load data | Anthony | Awaiting Customer | ENHC0015191 |  | \ | \ |  |  |  | 0
32531 | Feature | 2024-05-29 08:37 | Expanding the data that is being passed to us from People counter source via API |  | Steve | Active | ENHC0015195 | Tracy Chapman | \ | \
32631 | User Story | 2024-06-10 14:50 |  | Rob to look at the data integration API |  | Closed | ENHC0015195 |  | \ | \ |  |  |  | 0
33275 | User Story | 2024-08-05 10:10 |  | Gathering requirements | Steve | Closed | ENHC0015195 |  | \Lavender | \ |  |  | 4 | 0
34517 | User Story | 2024-10-24 12:34 |  | Expand people counter data | Steve | Closed | ENHC0015195 |  | \Poppy | \ |  | 5 | 5 | 0
34653 | User Story | 2024-11-06 10:11 |  | Develop SSIS integration | Steve | Active | ENHC0015195 |  | \Poppy | \ |  | 10 |  | 0
32669 | Feature | 2024-06-12 09:42 | Request Reports on People counter data |  |  | New | ENHC0015215 | Robert Downey | \ | \
32907 | Feature | 2024-07-03 09:30 | Concessions gross sales report - ADA compliant |  |  | On Hold | ENHC0015247 | Lawrence Taylor | \ | \
33011 | Feature | 2024-07-15 11:27 | Update Airline stats SSRS report to be ADA Compliant. |  |  | On Hold | ENHC0015257 | George Clooney | \ | \
33125 | User Story | 2024-07-22 10:32 |  | Create SSRS report for ADA Compliant | Harry | On Hold | ENHC0015257 |  | \ | \ |  |  |  | 0
33013 | Feature | 2024-07-16 09:55 | Add Search for the Fuel form and process |  |  | New | ENHC0015258 | Steve Martin | \ | \ |  |  |  | 2
34168 | User Story | 2024-10-02 14:10 |  | Gather Fuel requirements | Rachel | New | ENHC0015258 |  | \Poppy | \ |  | 2 | 0 | 0
33034 | Feature | 2024-07-16 11:33 | Non-Production Network Production/Inventory Values and Cost Estimation sheets need adjusting/correcting (use attached docs) |  |  | New | ENHC0015259 | Travis Barker | \ | \
33335 | Feature | 2024-08-09 17:38 | Add procurement data to data warehouse |  |  | On Hold | ENHC0015288 | Eliot Page | \ | \
34219 | User Story | 2024-10-07 10:41 |  | Provide advice to Procurement software | Steve | Closed | ENHC0015288 |  | \Zinnia | \ |  | 2 |  | 0
33367 | Feature | 2024-08-13 16:05 | Parking Data coming online from Contractor |  | Anthony | Active | ENHC0015292 | Bryan Adams | \ | \ |  |  |  | 2
33445 | User Story | 2024-08-20 15:16 |  | Research vendor docs and API requirements | Anthony | Closed | ENHC0015292 |  | \Hydrangea | \ |  |  |  | 0
33899 | User Story | 2024-09-20 09:52 |  | Map parking data file to existing parking table. | Anthony | Closed | ENHC0015292 |  | \Lavender | \ |  |  | 4 | 0
33967 | User Story | 2024-09-24 14:44 |  | Parking - Update SSIS Integration for Daily Transaction Data. | Anthony | Active | ENHC0015292 |  | \Poppy | \ |  | 30 | 10 | 0
33968 | User Story | 2024-09-24 14:46 |  | Develop SSIS integration for Occupancy Data - Near Realtime. | Anthony | New | ENHC0015292 |  | \ | \ |  |  |  | 0
33969 | User Story | 2024-09-24 14:47 |  | Update Tabular Model for Transaction Data. | Anthony | New | ENHC0015292 |  | \ | \ |  |  |  | 0
33706 | Feature | 2024-09-09 11:24 | Crisis Management Workflow API Call Proof of Concept/Documentation |  |  | On Hold | ENHC0015314 | Michael Myers | \Lavender | \
34114 | User Story | 2024-09-30 10:35 |  | Workflow data Integration from Crisis Management Software Workflow | Mary | On Hold | ENHC0015314 |  | \ | \ |  | 40 | 10 | 0
33880 | Feature | 2024-09-19 10:03 | Updates to Concession Incentive Program |  |  | New | ENHC0015326 | Lawrence Taylor | \ | \
33897 | Feature | 2024-09-20 08:50 | Review and update DW due to 'decustomizing' Maintnance source fields / Maintenance source reimplementation |  | Rachel | Active | ENHC0015327 | Michael Douglas | \ | \
34406 | User Story | 2024-10-18 11:00 |  | Maintenance source - Review technical document | Mary | Closed | ENHC0015327 |  | \Poppy | \ |  |  |  | 0
34589 | User Story | 2024-10-31 10:08 |  | Maven Sprint 2 development | Mary | Active | ENHC0015327 |  | \Poppy | \ |  | 160 | 16 | 0
33977 | Feature | 2024-09-24 16:04 | Create new data fields in Maintenance Data warehouse |  |  | New | ENHC0015351 | Eliot Page | \ | \
34314 | Feature | 2024-10-10 13:40 | Add concourse to Flight Schedule Analytical tabular model |  |  | New | ENHC0015381 | Tracy Chapman | \ | \
34334 | Feature | 2024-10-14 13:37 | PowerBI query from Finance Source |  |  | New | ENHC0015409 | Lawrence Taylor | \ | \ |  |  |  | 2
34347 | Feature | 2024-10-15 10:38 | Add a field to the Employee Extract file in the Database |  |  | New | ENHC0015410 | Renee Zellwegger | \ | \
34372 | Feature | 2024-10-15 13:53 | We need all of the Snow data from Crisis Management source moved into the Data Warehouse |  | Mary | Active | ENHC0015413 | Tracy Chapman | \ | \ |  |  |  | 2
34463 | User Story | 2024-10-23 13:29 |  | Crisis Management Source- Snow requirements gathering | Mary | New | ENHC0015413 |  | \Poppy | \ |  |  |  | 0
34410 | Feature | 2024-10-18 12:46 | Snow Deactivation data model from source to Power BI for DEN Snow Dashboard |  |  | New | ENHC0015418 | Derek Henry | \ | \
34433 | Feature | 2024-10-21 14:31 | Pull regulation data submissions into database so GIS team can access the data |  |  | New | ENHC0015425 | Chelesa Clinton | \ | \
34434 | Feature | 2024-10-21 17:21 | Biometric Exit dashboard request |  |  | New | ENHC0015426 | Eliot Page | \ | \
34436 | Feature | 2024-10-22 09:54 | In the Service Request Data Warehouse, need the "SENT TO" field created |  |  | New | ENHC0015428 | Matthew Broderick | \ | \
34457 | Feature | 2024-10-23 11:59 | Airport ops data extract to DEN BI data warehouse |  | Anthony | Active | ENHC0015432 | Robert Downey | \ | \
34464 | User Story | 2024-10-23 13:31 |  | Airport Ops - Research existing FIDS reports and requirements | Anthony | Active | ENHC0015432 |  | \Poppy | \ |  | 4 | 2 | 0
34568 | Feature | 2024-10-30 11:30 | CNG Crisis Management report |  | Mary | Active | ENHC0015443 | Bryan Adams | \ | \
34586 | Feature | 2024-10-31 08:06 | Load Screening Q3 data |  | Steve | Active | ENHC0015449 | James Murray | \Poppy | \
34587 | Feature | 2024-10-31 08:09 | Insurance data to Power BI |  | Steve | Active | ENHC0015450 | Derek Henry | \Poppy | \
34588 | Feature | 2024-10-31 08:10 | Products data cleanup |  | Steve | Active | ENHC0015451 | Lonnie Anderson | \Poppy | \
28052 | Feature | 2023-03-22 12:12 | Sustainability Dashboards |  | Mary | Closed | ENHC0014124 | James Murray | \ | \ |  |  |  | 2
26601 | User Story | 2022-07-01 15:15 |  | Greenhouse Gas Emissions Dashboard | Mary | Closed | ENHC0014124 |  | \Chrysanthemum | \ |  |  |  | 2
26603 | User Story | 2022-07-01 15:17 |  | Energy Sustainability Dashboard | Mary | Closed | ENHC0014126 |  | \ | \ |  |  |  | 2
30707 | User Story | 2024-01-04 09:29 |  | Compost and Trash Data Integration | Mary | Closed | ENHC0014124 |  | \Hibiscus | \ |  |  |  | 0
30712 | User Story | 2024-01-04 09:51 |  | User training on the Greenhouse dashboard | Mary | Closed | ENHC0014124 |  | \Hibiscus | \ |  |  |  | 0
30796 | User Story | 2024-01-12 10:32 |  | Jet Fuel Data | Mary | Closed | ENHC0014124 |  | \Gardenia | \ |  |  |  | 0
30797 | User Story | 2024-01-12 10:32 |  | Propane Gas Data | Mary | Closed | ENHC0014124 |  | \Gardenia | \ |  |  |  | 0
31041 | User Story | 2024-01-25 10:11 |  | Update Energy dashboards to remove Inforiver formatting | Mary | Closed | ENHC0014124 |  | \Orchid | \ |  |  |  | 0
31241 | User Story | 2024-02-06 11:06 |  | Combine all fuel sources into one dashboard | Mary | Closed | ENHC0014124 |  | \Gardenia | \ |  |  |  | 0
31893 | User Story | 2024-03-27 10:27 |  | Build Emission Dashboard | Mary | Closed | ENHC0014124 |  | \Orchid | \ |  |  |  | 0
28806 | Feature | 2023-06-12 10:59 | Upgrade to latest version - Connector 1 |  | Steve | Closed | ENHC0014775 | Rebecca DeMornay | \Jasmine | \
29299 | User Story | 2023-08-10 14:38 |  | Development | Steve | Closed | ENHC0014775 |  | \Jasmine | \ |  |  |  | 0
29793 | Feature | 2023-10-05 17:15 | Power BI dashboard for Network devices age |  |  | Closed | ENHC0014909 | Michael Keaton | \ | \
30097 | User Story | 2023-11-13 10:43 |  | Scoping - Power BI dashboard for Network devices age | Mel | Closed | ENHC0014909 |  | \Hibiscus | \ |  |  |  | 0
30789 | User Story | 2024-01-11 12:05 |  | Network Device Age - Build Dashboard | Mary | Closed | ENHC0014909 |  | \Dahlia | \ |  |  |  | 0
29816 | Feature | 2023-10-09 09:08 | Updates to concessions gross sales |  | Anthony | Closed | ENHC0014911 | Lawrence Taylor | \ | \ | Medium
30986 | User Story | 2024-01-23 12:44 |  | Updates to concessions gross sales | Anthony | Closed | ENHC0014911 |  | \ | \ |  |  |  | 0
32541 | User Story | 2024-05-29 13:07 |  | Deploy to PROD | Anthony | Closed | ENHC0014911 |  | \Lavender | \ |  |  |  | 0
31710 | Feature | 2024-03-12 23:01 | ADA Monthly Service Reports Automation |  |  | Closed | ENHC0015094 | Renee Zellwegger | \ | \
32688 | User Story | 2024-06-13 08:10 |  | Research / Gather Requirements | Harry | Closed | ENHC0015094 |  | \Lavender | \ |  |  |  | 0
33996 | User Story | 2024-09-26 10:38 |  | Development - ADA Vendor 1 Automation | Harry | Closed | ENHC0015094 |  | \Zinnia | \ |  | 5 | 5 | 0
34103 | User Story | 2024-09-30 08:57 |  | Development - ADA Vendor 2 Automation | Harry | Closed | ENHC0015094 |  | \Zinnia | \ |  | 10 | 10 | 0
34104 | User Story | 2024-09-30 08:57 |  | Development - ADA Kiosks Automation | Harry | Closed | ENHC0015094 |  | \Zinnia | \ |  | 20 | 25 | 0
34105 | User Story | 2024-09-30 08:58 |  | Development - ADA Vendor 3 Automation | Harry | Closed | ENHC0015094 |  | \Zinnia | \ |  | 20 | 15 | 0
32321 | Feature | 2024-05-02 13:23 | We need to pull data from the parking vendor into the data warehouse to enable regular reporting on Parking Lot Capacity |  |  | Closed | ENHC0015163 | Tracy Chapman | \Tulip | \ |  |  |  |  | 2024-05-12 18:00
32413 | User Story | 2024-05-14 09:58 |  | Research data | Anthony | Closed | ENHC0015163 |  | \Tulip | \ |  | 1 |  | 0
32540 | User Story | 2024-05-29 12:50 |  | Pull data into the warehouse | Mary | Closed | ENHC0015163 |  | \Dahlia | \ |  |  |  | 0
32702 | User Story | 2024-06-17 10:33 |  | UAT - Parking stats | Mary | Closed | ENHC0015163 |  | \Daffodil | \ |  |  |  | 0
32813 | User Story | 2024-06-25 13:41 |  | Production Deployment - Parking Stats | Mary | Closed | ENHC0015163 |  | \Daffodil | \ |  |  |  | 0
32338 | Feature | 2024-05-07 08:46 | Self Bagdrop Dashboard Enhancement |  |  | Closed | ENHC0015169 | Nate Bargatze | \ | \
32358 | User Story | 2024-05-07 14:39 |  | Add additional dashboards | Mary | Closed | ENHC0015169 |  | \Tulip | \ |  |  |  | 0
32416 | Feature | 2024-05-14 11:47 | Maintenance software rehosting testing |  |  | Closed | ENHC0015179 | Russell Peters | \ | \
32417 | User Story | 2024-05-14 11:49 |  | Maintenance Software connectivity testing | Steve | Closed | ENHC0015179 |  | \Dahlia | \ |  |  |  | 0
32536 | Feature | 2024-05-29 10:11 | Add Previous Week Page Report to OPS Ramp Tower Metrics |  |  | Closed | ENHC0015196 | Renee Zellwegger | \ | \
32537 | Feature | 2024-05-29 10:13 | OPS On Time Performance Report |  |  | Closed | ENHC0015197 | Lawrence Taylor | \ | \
32538 | Feature | 2024-05-29 10:15 | OPS TSA Checkpoint Wait Times |  |  | Closed | ENHC0015198 | Michael Douglas | \ | \
32691 | Feature | 2024-06-13 12:01 | Microsoft Fabric POC |  |  | Closed | ENHC0015218 | Chris Martin | \ | \
33446 | User Story | 2024-08-20 15:18 |  | Complete Tutorials | Steve | Closed | ENHC0015218 |  | \Hydrangea | \ |  |  |  | 0
33447 | User Story | 2024-08-20 15:18 |  | Complete Tutorials | Anthony | Closed | ENHC0015218 |  | \Hydrangea | \ |  |  |  | 0
33448 | User Story | 2024-08-20 15:18 |  | Complete Tutorials | Mary | Closed | ENHC0015218 |  | \Hydrangea | \ |  |  |  | 0
33449 | User Story | 2024-08-20 15:20 |  | Complete Tutorials | Harry | Closed | ENHC0015218 |  | \Hydrangea | \ |  |  |  | 0
33683 | User Story | 2024-09-06 09:40 |  | ML workshop |  | Closed | ENHC0015218 |  | \Lavender | \ |  |  |  | 0
33684 | User Story | 2024-09-06 09:40 |  | GenAI workshop |  | Closed | ENHC0015218 |  | \Lavender | \ |  |  |  | 0
32692 | Feature | 2024-06-13 12:07 | Microsoft Purview POC - Data Quality |  |  | Closed | ENHC0015220 | Chris Martin | \ | \
33329 | User Story | 2024-08-09 11:49 |  | Microsoft Purview POC - Data Quality | Rachel | Closed | ENHC0015220 |  | \Hydrangea | \ |  |  |  | 0
32964 | Feature | 2024-07-09 10:38 | AskIT/ServiceNow fields imported into the Data Warehouse. |  |  | Closed | ENHC0015249 | Renee Zellwegger | \ | \
33012 | User Story | 2024-07-15 11:52 |  | Research | Mary | Closed | ENHC0015249 |  | \Jasmine | \ |  |  |  | 0
33218 | Feature | 2024-07-31 11:56 | BI reports from Finance source for cash posting |  |  | Closed | ENHC0015273 | Michael Douglas | \ | \
33330 | User Story | 2024-08-09 11:52 |  | Cash Posting Finance source | Steve | Closed | ENHC0015273 |  | \Hydrangea | \ |  |  |  | 0
34315 | Feature | 2024-10-10 13:56 | Maintenance Division data collection and analysis for Q3/V.100 |  |  | Closed | ENHC0015382 | Bryan Adams | \ | \
34316 | Feature | 2024-10-10 14:02 | Maintenance Division data analytics for Q3/Vision100 |  |  | Closed | ENHC0015387 | Eliot Page | \ | \

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter | \ | \ | Select User... | Select User... | Active | High | 1 | Active | 1 | Select User... | Active | 1 | Select User... | Active | High | 1 | Select User... | Active | 1 | Select User... | Active | 0 | Select User... | Closed | 1 | Select User... | Active | 0 | Bug | Select User... | Active | 1 | High
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_M/d/yyyy h:mm AM/PM | readOnlyTestRange_General | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_System.AreaPath | \Armenia | Anju Mohan | Anju Mohan | Closed | Low | 2 | Blocked | 2 | Anju Mohan | Closed | 2 | Anju Mohan | Closed | Low | 2 | Anju Mohan | Closed | 2 | Anju Mohan | Blocked | 1 | Anju Mohan | Design | 2 | Anju Mohan | Approved | 1 | Epic | Anju Mohan | Blocked | 2 | Low
[5 empty] | \Azalea | Bass, Melanie - DEN | AskIT Azure | New | Medium | 3 | Closed | 3 | AskIT Azure | New | 3 | AskIT Azure | New | Medium | 3 | AskIT Azure | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Issue_System.State | 3 | AskIT Azure | Closed | 2 | AskIT Azure | Ready | 3 | AskIT Azure | Awaiting Approval | 2 | Feature | Bass, Melanie - DEN | Closed | 3 | Medium
[5 empty] | \Bolivia | Cain, Nate - DEN | Bass, Melanie - DEN | On Hold | VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_17-2D-C0-DC-6F-4F-D9-60-21-AA-42-B5-B1-41-B8-90-71-EA-A4-89 | 4 | Deferred | 4 | Bass, Melanie - DEN | Removed | 4 | Bass, Melanie - DEN | On Hold | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Feature_Custom.LevelofEffort | 4 | Bass, Melanie - DEN |  | 4 | Bass, Melanie - DEN | New | 3 | Bass, Melanie - DEN | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Test Case_System.State | 4 | Bass, Melanie - DEN | Awaiting Customer | 3 | Issue | Cain, Nate - DEN | Deferred | 4 | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Custom.LevelofEffort
[5 empty] | \Carnation | Chris Schulz | Cain, Nate - DEN | Removed |  | VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_A9-74-3C-60-20-83-BF-D2-70-44-DA-6E-AF-8C-55-96-9A-24-CE-B3 | Duplicate | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Bug_Microsoft.VSTS.Common.Priority | Cain, Nate - DEN | Resolved | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Epic_Microsoft.VSTS.Common.Priority | Cain, Nate - DEN | Removed |  | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Feature_Microsoft.VSTS.Common.Priority | Cain, Nate - DEN |  | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Issue_Microsoft.VSTS.Common.Priority | Cain, Nate - DEN | Removed | 4 | Cain, Nate - DEN |  | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Test Case_Microsoft.VSTS.Common.Priority | Cain, Nate - DEN | Backlog | 4 | Task | Chris Schulz | Duplicate | 0
[5 empty] | \Chad | Damon Haastrup | Chris Schulz | Resolved |  |  | New |  | Chris Schulz | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Epic_System.State |  | Chris Schulz | Resolved |  |  | Chris Schulz |  |  | Chris Schulz | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Task_System.State | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Task_Microsoft.VSTS.Common.Priority | Chris Schulz |  |  | Chris Schulz | Blocked | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_User Story_Microsoft.VSTS.Common.Priority | Test Case | Damon Haastrup | New | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Microsoft.VSTS.Common.Priority
[5 empty] | \Chrysanthemum | DeSantis, Rebecca - DEN | Damon Haastrup | VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_EF-53-4E-3E-4A-AF-17-9B-79-6E-C6-A3-D6-FD-66-4A-C7-0E-4F-A1 |  |  | Rejected |  | Damon Haastrup |  |  | Damon Haastrup | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Feature_System.State |  |  | Damon Haastrup |  |  | Damon Haastrup |  |  | Damon Haastrup |  |  | Damon Haastrup | Cancelled |  | User Story | DeSantis, Rebecca - DEN | Rejected
[5 empty] | \Daffodil | Hobart, Craig - DEN | DeSantis, Rebecca - DEN |  |  |  | Resolved |  | DeSantis, Rebecca - DEN |  |  | DeSantis, Rebecca - DEN |  |  |  | DeSantis, Rebecca - DEN |  |  | DeSantis, Rebecca - DEN |  |  | DeSantis, Rebecca - DEN |  |  | DeSantis, Rebecca - DEN | Closed |  | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_System.WorkItemType | Hobart, Craig - DEN | Resolved
[5 empty] | \Dahlia | Moukadem, Malek | Hobart, Craig - DEN |  |  |  | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Bug_System.State |  | Hobart, Craig - DEN |  |  | Hobart, Craig - DEN |  |  |  | Hobart, Craig - DEN |  |  | Hobart, Craig - DEN |  |  | Hobart, Craig - DEN |  |  | Hobart, Craig - DEN | Deployment |  |  | Moukadem, Malek | Removed
[5 empty] | \Dominican Republic | Prashanth Arumalla | Kumar, Hariharan - DEN | [5 empty] | Kumar, Hariharan - DEN |  |  | Kumar, Hariharan - DEN |  |  |  | Kumar, Hariharan - DEN |  |  | Kumar, Hariharan - DEN |  |  | Kumar, Hariharan - DEN |  |  | Kumar, Hariharan - DEN | New |  |  | Prashanth Arumalla | On Hold
[5 empty] | \Egypt | Rajyalakshmi Chava | Moukadem, Malek | [5 empty] | Moukadem, Malek |  |  | Moukadem, Malek |  |  |  | Moukadem, Malek |  |  | Moukadem, Malek |  |  | Moukadem, Malek |  |  | Moukadem, Malek | On Hold |  |  | Rajyalakshmi Chava | Design
[5 empty] | \France | Ramos, Tabitha - DEN | Prashanth Arumalla | [5 empty] | Prashanth Arumalla |  |  | Prashanth Arumalla |  |  |  | Prashanth Arumalla |  |  | Prashanth Arumalla |  |  | Prashanth Arumalla |  |  | Prashanth Arumalla | Removed |  |  | Ramos, Tabitha - DEN | Ready
[5 empty] | \Gardenia | Stone, Deneen - DEN | Rajyalakshmi Chava | [5 empty] | Rajyalakshmi Chava |  |  | Rajyalakshmi Chava |  |  |  | Rajyalakshmi Chava |  |  | Rajyalakshmi Chava |  |  | Rajyalakshmi Chava |  |  | Rajyalakshmi Chava | Resolved |  |  | Stone, Deneen - DEN | Approved
[5 empty] | \Hibiscus | Wieben, Matthew - DEN | Ramos, Tabitha - DEN | [5 empty] | Ramos, Tabitha - DEN |  |  | Ramos, Tabitha - DEN |  |  |  | Ramos, Tabitha - DEN |  |  | Ramos, Tabitha - DEN |  |  | Ramos, Tabitha - DEN |  |  | Ramos, Tabitha - DEN | Testing |  |  | Wieben, Matthew - DEN | Awaiting Approval
[5 empty] | \Hydrangea | Woods, Robin - DEN | Stone, Deneen - DEN | [5 empty] | Stone, Deneen - DEN |  |  | Stone, Deneen - DEN |  |  |  | Stone, Deneen - DEN |  |  | Stone, Deneen - DEN |  |  | Stone, Deneen - DEN |  |  | Stone, Deneen - DEN | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_User Story_System.State |  |  | Woods, Robin - DEN | Awaiting Customer
[5 empty] | \Iteration 2 | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Bug_System.AssignedTo | Wieben, Matthew - DEN | [5 empty] | Wieben, Matthew - DEN |  |  | Wieben, Matthew - DEN |  |  |  | Wieben, Matthew - DEN |  |  | Wieben, Matthew - DEN |  |  | Wieben, Matthew - DEN |  |  | Wieben, Matthew - DEN |  |  |  |  | Backlog
[5 empty] | \Iteration 3 |  | Woods, Robin - DEN | [5 empty] | Woods, Robin - DEN |  |  | Woods, Robin - DEN |  |  |  | Woods, Robin - DEN |  |  | Woods, Robin - DEN |  |  | Woods, Robin - DEN |  |  | Woods, Robin - DEN |  |  |  | Kumar, Hariharan - DEN | Cancelled
[5 empty] | \Jasmine |  | VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_9D-06-4D-E7-5E-0C-36-C3-FD-73-C1-13-6A-3B-BC-39-B4-BC-A3-BA | [5 empty] | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Epic_System.AssignedTo |  |  | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Feature_System.AssignedTo |  |  |  | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Issue_System.AssignedTo |  |  | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Task_System.AssignedTo |  |  | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_Test Case_System.AssignedTo |  |  | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_User Story_System.AssignedTo |  |  |  | AskIT Azure | Deployment
[5 empty] | \Lavender | [27 empty] | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_System.AssignedTo | Testing
[5 empty] | \Lily | [28 empty] | all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_System.State
\Orchid
\Peony
\Poppy
\Qatar
\Romania
\Rose
\Spain
\SQL environment - HSS
\SQL environment - ISS
\Sunflower
\Tanzania
\Tulip
\Ukraine
\Venezuela
\West Indies
\Yemen
\Zambia
\Zinnia
all_VSTS_12f86f82_d634_4c6d_8aaf_71c7fb2ea221_System.IterationPath