## Sheet1
Number | Opened | Updated | Assignment group | Assigned to | Short description | Azure DevOps Id | State | Opened by | Requested For | Application | Priority | Due date | days_delta
ENHC0015432 | 2024-10-23 11:57 | 2024-10-25 01:04 | Business Intelligence | Anthony | Airport Ops AODB data extract to DEN BI datawarehouse | 34457 | Work in Progress |  | Anne Murray | Data Analytics | 5 - Planning | 2025-04-09 20:34 | 168.3589
ENHC0015413 | 2024-10-15 13:51 | 2024-10-24 12:46 | Business Intelligence | Mary | We need all of the Snow data from Crisis Management Source moved into the Data Warehouse | 34372 | Work in Progress |  | George Clooney | Data Analytics | 5 - Planning | 2025-02-07 10:17 | 114.8512
ENHC0015351 | 2024-09-24 16:01 | 2024-09-24 16:04 | Business Intelligence | Anthony | Create new data fields in Maintenance Source Asset Data warehouse | 33977 | Draft |  | Chris Martin | Data Analytics | 5 - Planning | 2025-02-19 11:04 | 147.7936
ENHC0015327 | 2024-09-20 08:50 | 2024-10-25 01:04 | Business Intelligence | Rachel | Review and update DW due to 'decustomizing' Maintenance Source fields / Maintenance Source reimplementation | 33897 | Work in Progress |  | Jake From StateFarm | Data Analytics | 5 - Planning | 2025-03-21 07:10 | 181.9306
ENHC0015273 | 2024-07-30 10:36 | 2024-10-24 12:48 | Business Intelligence | Steven | BI reports from Finance Source for cash posting | 33218 | Closed Complete |  | Anthony Hopkins | Data Analytics | 5 - Planning | 2025-01-13 05:28 | 166.7863
ENHC0015220 | 2024-06-13 12:04 | 2024-09-04 00:01 | Business Intelligence | Rachel | Microsoft Purview POC - Data Quality | 32692 | Closed Complete |  | Tina Fey | Data Analytics | 5 - Planning | 2024-09-24 06:04 | 102.7499
ENHC0015215 | 2024-06-12 09:39 | 2024-10-09 09:20 | Business Intelligence | Anthony | Request Reports on People Counter data | 32669 | Draft |  | Michelle Obama | Data Analytics | 5 - Planning | 2024-07-30 04:40 | 47.7921
ENHC0015139 | 2024-04-17 13:39 | 2024-05-07 00:02 | Business Intelligence | Steven | Data Analytics team to migrate to Secret Server | 32176 | Closed Complete |  | Joy Behar | Data Analytics | 5 - Planning | 2024-05-28 10:07 | 40.8528
ENHC0015113 | 2024-03-26 12:00 | 2024-05-24 00:02 | Business Intelligence | Mary | Clean up tabular models | 31883 | Closed Complete |  | Renee Russell | Data Analytics | 5 - Planning | 2024-06-09 04:41 | 74.6951
ENHC0015029 | 2024-01-29 10:45 | 2024-02-16 00:01 | Business Intelligence | Steven | Level 6 West security checkpoint - update dashboards | 31066 | Closed Complete |  | Matthew Broderick | Data Analytics | 5 - Planning | 2024-06-09 08:57 | 131.925
ENHC0015003 | 2024-01-11 13:13 | 2024-04-02 14:52 | Business Intelligence | Anthony | Need a little help creating a measure for a power bi report | 30790 | Closed Complete |  | Michelle Obama | Data Analytics | 5 - Planning | 2024-01-17 00:12 | 5.4576
ENHC0014681 | 2023-05-11 13:30 | 2023-08-04 09:16 | Business Intelligence | Anthony | Migrate Cab data to new Azure tenant | 28514 | Closed Complete |  | Scott Bakula | Data Analytics | 5 - Planning | 2023-10-06 02:54 | 147.5587
ENHC0014633 | 2023-04-26 13:28 | 2023-05-11 13:36 | Business Intelligence | Anthony | Change BI FIDS and Rideshare data source to new Azure Tenant. | 28356 | Closed Complete |  | Sade | Data Analytics | 5 - Planning | 2023-06-04 02:15 | 38.5332
ENHC0014490 | 2023-02-15 11:52 | 2023-03-22 12:57 | Business Intelligence | Anthony | Rideshare DB Data Access |  | Closed Complete |  | John Mayer | Data Analytics | 3 - Moderate | 2023-04-20 22:41 | 64.4504
ENHC0014438 | 2023-01-31 14:21 | 2023-05-15 10:46 | Business Intelligence | Mary | Add Maintenance Source Service Requests into data warehouse | 27579 | Closed Complete |  | Amy Winehouse | Data Analytics | 5 - Planning | 2023-01-03 14:02 | -28.0135
ENHC0014324 | 2022-11-15 17:10 | 2024-01-09 19:31 | Business Intelligence | Mary | Looking for a report of onboarding and offboarding activity | 27205 | Closed Complete | Amy Winehouse | Amy Winehouse | Data Analytics | 5 - Planning | 2023-02-18 21:29 | 95.1798
ENHC0014921 | 2023-10-24 09:28 | 2024-02-16 00:01 | Business Intelligence | Steven | Updates to Screening data | 29954 | Closed Complete | Anne Murray | Anne Murray | Data Analytics | 5 - Planning | 2024-04-18 08:03 | 176.9409
ENHC0014394 | 2023-01-18 13:44 | 2023-07-13 10:56 | Business Intelligence | Mary | Replace the "slicer" / lookup for conveyance from a list of conveyance assets to a lookup table based on building from bim code. | 27451 | Closed Complete | Anthony Hopkins | Anthony Hopkins | Data Analytics | 5 - Planning | 2023-06-19 15:59 | 152.0938
ENHC0015171 | 2024-05-08 11:48 | 2024-09-19 13:09 | Business Intelligence | Mel | Capture concessionaire transaction data in the concessions warehouse. | 32364 | Work in Progress | Branden Flowers | Branden Flowers | Data Analytics | 5 - Planning | 2024-08-13 02:42 | 96.6206
ENHC0014899 | 2023-09-21 09:15 | 2023-11-13 10:06 | Business Intelligence | Anthony | auditor's office request - Concessions Report | 29675 | Closed Complete | Branden Flowers | Branden Flowers | Data Analytics | 5 - Planning | 2024-01-18 06:37 | 118.8897
ENHC0014455 | 2023-02-02 09:47 | 2024-05-29 14:32 | Business Intelligence | Anthony | Compensation rates are not populating in Concessions reports. | 27621 | Work in Progress | Branden Flowers | Branden Flowers | Data Analytics | 5 - Planning | 2023-02-13 14:42 | 11.2047
ENHC0014448 | 2023-02-01 06:41 | 2023-12-05 19:26 | Business Intelligence | Rachel | Updates to the Assessor's report | 27580 | Closed Complete | Branden Flowers | Branden Flowers | Data Analytics | 5 - Planning | 2023-02-26 15:20 | 25.3603
ENHC0015292 | 2024-08-13 16:03 | 2024-10-24 12:47 | Business Intelligence | Anthony | Parking Data coming online from Contractor | 33367 | Work in Progress | Bryan Adams | Bryan Adams | Data Analytics | 5 - Planning | 2024-10-09 16:09 | 57.004
ENHC0015103 | 2024-03-18 15:05 | 2024-09-19 14:11 | Business Intelligence | Mel | Parking - Rideshare 10 or 15 min granular level of detail | 31828 | Draft | Bryan Adams | Bryan Adams | Data Analytics | 5 - Planning | 2024-05-03 22:17 | 46.2998
ENHC0015102 | 2024-03-18 14:40 | 2024-09-19 14:11 | Business Intelligence | Rachel | Parking - Add Forecasting capability to Parking and Transportation dashboards | 31827 | Draft | Bryan Adams | Bryan Adams | Data Analytics | 5 - Planning | 2024-05-13 03:13 | 55.5225
ENHC0015101 | 2024-03-18 13:32 | 2024-09-10 17:03 | Business Intelligence | Harry | Parking - Combine the Revenue and Transaction By lot into one | 31826 | Closed Complete | Bryan Adams | Bryan Adams | Data Analytics | 5 - Planning | 2024-05-20 18:58 | 63.226
ENHC0015100 | 2024-03-18 10:46 | 2024-09-10 17:03 | Business Intelligence | Rachel | Fix the Parking Duration in Minutes under the Duration tab | 31821 | Closed Complete | Bryan Adams | Bryan Adams | Data Analytics | 5 - Planning | 2024-08-31 20:19 | 166.3977
ENHC0015005 | 2024-01-12 08:49 | 2024-01-29 10:49 | Business Intelligence | Anthony | Shuttle Reports based on data from vendor | 30795 | Draft | Bryan Adams | Bryan Adams | Data Analytics | 5 - Planning | 2024-05-13 17:28 | 122.3603
ENHC0014544 | 2023-03-20 07:48 | 2023-04-05 13:26 | Business Intelligence | Anthony | Add TSA forecast data to Data Warehouse. | 27989 | Closed Complete | Bryan Adams | Bryan Adams | Data Analytics | 5 - Planning | 2023-05-15 10:59 | 56.1332
ENHC0014366 | 2022-12-19 10:35 | 2023-03-15 09:46 | Business Intelligence | Anthony | Create reports for Commercial Transportation. | 27357 | Closed Complete | Bryan Adams | Bryan Adams | Data Analytics | 5 - Planning | 2023-03-06 04:33 | 76.7491
ENHC0014923 | 2023-10-27 13:20 | 2024-03-07 00:01 | Business Intelligence | Steven | Vendor EBI data integration | 29987 | Closed Complete | Charlotte Church | Charlotte Church | Data Analytics | 5 - Planning | 2024-03-02 20:39 | 127.3053
ENHC0015425 | 2024-10-21 14:23 | 2024-10-21 14:31 | Business Intelligence | Rachel | Pull regulation data submissions into database so GIS team can access the data | 34433 | Draft | Chelsea Clinton | Chelsea Clinton | Data Analytics | 5 - Planning | 2024-08-16 01:26 | -66.5392
ENHC0014783 | 2023-06-20 11:47 | 2024-10-08 15:29 | Business Intelligence | Anthony | Migrate Pena traffic data from source to prod | 28848 | On Hold | Chelsea Clinton | Chelsea Clinton | Data Analytics | 5 - Planning | 2023-09-21 11:20 | 92.9811
ENHC0014315 | 2022-11-09 11:27 | 2024-09-26 12:13 | Business Intelligence | Rachel | Update for Snow Reporting dashboard import process. | 27133 | Closed Complete | Chris Martin | Chris Martin | Data Analytics | 5 - Planning | 2022-12-25 17:12 | 46.2394
ENHC0014955 | 2023-12-04 10:24 | 2024-01-30 00:01 | Business Intelligence | Steven | Updates to OTP in flight ops | 30245 | Closed Complete | Christopher Nolan | Christopher Nolan | Data Analytics | 5 - Planning | 2024-04-25 16:15 | 143.2439
ENHC0014811 | 2023-07-10 10:40 | 2023-09-19 10:41 | Business Intelligence | Mary | Flight Schedule Data Enhancement | 28968 | Closed Complete | Christopher Nolan | Christopher Nolan | Data Analytics | 5 - Planning | 2023-09-09 18:53 | 61.3424
ENHC0015418 | 2024-10-18 12:45 | 2024-10-18 12:50 | Business Intelligence | Anthony | Snow Deactivation data model from source to Power BI for DEN Snow Dashboard | 34410 | Draft | Derek Henry | Derek Henry | Data Analytics | 5 - Planning | 2024-12-07 08:49 | 49.8361
ENHC0014323 | 2022-11-15 10:53 | 2023-03-23 14:41 | Business Intelligence | Mary | Business Intelligence ServiceNow database's survey data is not matching with AskIT report. | 28048 | Closed Complete | Ed Harris | Ed Harris | Data Analytics | 3 - Moderate | 2023-04-09 02:27 | 144.6486
ENHC0015288 | 2024-08-09 17:37 | 2024-10-16 01:01 | Business Intelligence | Anthony | Add Procurement software data to data warehouse | 33335 | On Hold | Eliot Page | Eliot Page | Data Analytics | 5 - Planning | 2024-12-10 07:09 | 122.5639
ENHC0014789 | 2023-06-26 09:36 | 2023-09-19 10:37 | Business Intelligence | Steven | Updates to Contract Management | 28876 | Closed Complete | Eliot Page | Eliot Page | Data Analytics | 5 - Planning | 2024-01-10 10:14 | 198.0262
ENHC0014613 | 2023-04-17 11:19 | 2023-07-31 13:16 | Business Intelligence | Mary | Power BI Calculation formula | 28266 | Closed Complete | Evelyn Rose | Evelyn Rose | Data Analytics | 5 - Planning | 2023-06-14 12:21 | 58.0435
ENHC0014683 | 2023-05-12 11:26 | 2023-09-19 11:44 | Business Intelligence | Mary | Add first name, last name, and display name linked to reported by on service request table in service request model | 28525 | Closed Complete | Frankie Goes to Hollywood | Frankie Goes to Hollywood | Data Analytics | 5 - Planning | 2023-07-24 19:00 | 73.3156
ENHC0014314 | 2022-11-08 12:24 | 2023-06-01 10:46 | Business Intelligence | Mary | Update to Work Order Tabular Model | 27130 | Closed Complete | Frankie Goes to Hollywood | Frankie Goes to Hollywood | Data Analytics | 5 - Planning | 2023-01-15 15:17 | 68.1199
ENHC0015257 | 2024-07-15 11:25 | 2024-10-17 01:02 | Business Intelligence | Harry | Update Airline stats SSRS report to be ADA Compliant. | 33011 | On Hold | George Clooney | George Clooney | Data Analytics | 5 - Planning | 2024-07-10 04:28 | -5.2897
ENHC0014638 | 2023-04-27 11:30 | 2023-06-12 15:54 | Business Intelligence | Mel | PowerBI dashboard for Airport Planning | 28371 | Closed Complete | Gil Grissom | Gil Grissom | Data Analytics | 5 - Planning | 2023-05-26 00:41 | 28.549
ENHC0014930 | 2023-11-02 09:38 | 2024-08-30 00:01 | Business Intelligence | Steven | Service Desk dashboards | 30022 | Work in Progress | Jake From StateFarm | Jake From StateFarm | Data Analytics | 5 - Planning | 2024-03-11 03:31 | 129.7449
ENHC0014828 | 2023-07-19 17:56 | 2024-09-19 14:36 | Business Intelligence | Steven | FCR (fist contact resolution) Service now report and power BI dashboard. | 29038 | Backlog | Jake From StateFarm | Jake From StateFarm | Data Analytics | 5 - Planning | 2023-08-20 17:20 | 31.9746
ENHC0014799 | 2023-06-29 10:27 | 2024-05-16 11:57 | Business Intelligence | Steven | Updates to Insurance and Surety letters for Concessions | 28908 | Closed Complete | Jessica Day | Jessica Day | Data Analytics | 5 - Planning | 2023-10-24 17:43 | 117.3028
ENHC0014596 | 2023-04-05 15:55 | 2023-08-16 09:06 | Business Intelligence | Mel | Juan's BT Dashboard - update to Service Requests | 28166 | Closed Complete | John Mayer | John Mayer | Data Analytics | 5 - Planning | 2023-08-31 19:50 | 148.1629
ENHC0014733 | 2023-05-18 13:43 | 2023-07-13 14:06 | Business Intelligence | Anthony | Add BT project hierarchy from SharePoint list to CIP Power BI report. | 28625 | Closed Complete | Joy Behar | Joy Behar | Data Analytics | 5 - Planning | 2023-09-18 12:22 | 122.9439
ENHC0015035 | 2024-01-31 07:55 | 2024-10-17 01:01 | Business Intelligence | Rachel | Controls project | 31125 | On Hold | Larry Wilmore | Larry Wilmore | Data Analytics | 5 - Planning | 2024-05-26 12:21 | 116.1845
ENHC0014919 | 2023-10-23 13:35 | 2023-12-05 19:27 | Business Intelligence | Steven | Automate Passenger Capacity Data Retrieval | 29949 | Closed Complete | Laura Dern | Laura Dern | Data Analytics | 5 - Planning | 2024-03-27 22:10 | 156.3578
ENHC0015409 | 2024-10-14 13:30 | 2024-10-14 13:39 | Business Intelligence | Anthony | PowerBI query from Finance Source | 34334 | Draft | Lawrence Taylor | Lawrence Taylor | Data Analytics | 5 - Planning | 2025-03-09 04:32 | 145.6262
ENHC0015326 | 2024-09-19 10:01 | 2024-09-19 12:46 | Business Intelligence | Anthony | Updates to Concession Incentive Program | 33880 | Draft | Lawrence Taylor | Lawrence Taylor | Data Analytics | 5 - Planning | 2024-10-25 16:28 | 36.2685
ENHC0015247 | 2024-07-03 09:29 | 2024-10-17 01:02 | Business Intelligence | Steven | Concessions gross sales report - ADA compliant | 32907 | On Hold | Lawrence Taylor | Lawrence Taylor | Data Analytics | 5 - Planning | 2024-10-18 13:35 | 107.1708
ENHC0014987 | 2024-01-05 12:27 | 2024-02-16 00:01 | Business Intelligence | Steven | concessions compensation and gross sales from 2005 to current | 30747 | Closed Complete | Lawrence Taylor | Lawrence Taylor | Data Analytics | 5 - Planning | 2024-05-23 18:59 | 139.2719
ENHC0014911 | 2023-10-09 09:05 | 2024-10-25 01:02 | Business Intelligence | Anthony | Updates to concessions gross sales | 29816 | Closed Complete | Lawrence Taylor | Lawrence Taylor | Data Analytics | 5 - Planning | 2024-02-13 04:53 | 126.8251
ENHC0014541 | 2023-03-15 14:11 | 2023-12-05 19:26 | Business Intelligence | Steven | Sales data - pulling from Finance Source | 27957 | Closed Complete | Lawrence Taylor | Lawrence Taylor | Data Analytics | 5 - Planning | 2023-03-01 13:38 | -14.0231
ENHC0014782 | 2023-06-15 13:06 | 2023-09-19 10:38 | Business Intelligence | Steven | Convert Crystal report to SSRS | 28837 | Closed Complete | Lisa Bonet | Lisa Bonet | Data Analytics | 5 - Planning | 2023-08-29 14:48 | 75.0707
ENHC0014481 | 2023-02-13 09:16 | 2023-03-20 09:16 | Business Intelligence | Steven | Convert plumbing crystal reports to SSRS | 27684 | Closed Complete | Lisa Bonet | Lisa Bonet | Data Analytics | 5 - Planning | 2023-02-16 22:13 | 3.5395
ENHC0014379 | 2023-01-04 14:32 | 2023-08-16 09:26 | Business Intelligence | Steven | All-Active Contracts Report (Future State) | 27867 | Closed Complete | Lisa Bonet | Lisa Bonet | Data Analytics | 5 - Planning | 2023-04-04 18:45 | 90.1755
ENHC0015170 | 2024-05-08 10:05 | 2024-09-19 13:09 | Business Intelligence | Mary | Parking - Lost and Found Dashboard | 32363 | Draft | Mark Cuban | Mark Cuban | Data Analytics | 5 - Planning | 2024-11-11 03:36 | 186.7298
ENHC0015428 | 2024-10-22 09:52 | 2024-10-22 10:17 | Business Intelligence | Harry | In the Service Request Data Warehouse, need the "SENT TO" field created | 34436 | Draft | Mark Wahlberg | Mark Wahlberg | Data Analytics | 5 - Planning | 2025-01-31 06:56 | 100.878
ENHC0015072 | 2024-02-27 13:03 | 2024-03-22 00:01 | Business Intelligence | Steven | Updates to Monitors Dashboard App | 31499 | Closed Complete | Mary Enough | Mary Enough | Data Analytics | 5 - Planning | 2024-08-26 02:20 | 180.5541
ENHC0015191 | 2024-05-23 11:25 | 2024-10-08 15:29 | Business Intelligence | Rachel | Baggage Handling System data into the DEN Data Warehouse | 32519 | On Hold | Matthew Broderick | Matthew Broderick | Data Analytics | 5 - Planning | 2024-04-16 00:08 | -37.4697
ENHC0014938 | 2023-11-14 11:07 | 2024-04-05 00:02 | Business Intelligence | Mary | Updated Snow Dashboard with Contract Companies | 30120 | Closed Complete | Matthew Broderick | Matthew Broderick | Data Analytics | 5 - Planning | 2024-02-02 04:22 | 79.7191
ENHC0014906 | 2023-10-04 09:17 | 2024-09-19 14:30 | Business Intelligence | Steven | New measure for train system | 31596 | Draft | Matthew Broderick | Matthew Broderick | Data Analytics | 5 - Planning | 2024-01-02 20:31 | 90.4682
ENHC0014739 | 2023-05-22 14:43 | 2023-09-11 13:36 | Business Intelligence | Steven | BI/Analytics - Data refresh solution to replace use of Personal Gateway | 28725 | Closed Complete | Matthew Broderick | Matthew Broderick | Data Analytics | 5 - Planning | 2023-05-01 13:44 | -21.0412
ENHC0014623 | 2023-04-24 08:38 | 2023-09-21 10:56 | Business Intelligence | Mary | BI Team - Integration of hourly TSA throughput data into the enterprise data warehouse via Teams | 28312 | Closed Complete | Matthew Broderick | Matthew Broderick | Data Analytics | 5 - Planning | 2023-06-10 02:02 | 46.7251
ENHC0014543 | 2023-03-17 08:54 | 2024-09-25 10:58 | Business Intelligence | Mary | update POT usage report in powerbi with detail info | 27976 | Closed Complete | Matthew Broderick | Matthew Broderick | Data Analytics | 5 - Planning | 2023-06-09 13:53 | 84.2074
ENHC0014517 | 2023-03-07 05:22 | 2024-09-26 12:14 | Business Intelligence | Mary | Add another data field to the Power BI dashboard on snow metrics for Maintenance | 27859 | Closed Complete | Matthew Broderick | Matthew Broderick | Data Analytics | 5 - Planning | 2023-06-10 22:39 | 95.7205
ENHC0014507 | 2023-03-01 13:04 | 2023-04-05 13:26 | Business Intelligence | Anthony | Additional measures/changes to the FIDS FlightDetails model | 27786 | Closed Complete | Matthew Broderick | Matthew Broderick | Data Analytics | 5 - Planning | 2023-05-27 14:58 | 87.0791
ENHC0014478 | 2023-02-09 11:21 | 2023-03-14 14:02 | Business Intelligence | Anthony | Flight Operations model not refreshing by 0800 | 27675 | Closed Complete | Matthew Broderick | Matthew Broderick | Data Analytics | 2 - High | 2023-06-10 13:58 | 121.1094
ENHC0014434 | 2023-01-30 11:11 | 2023-02-22 10:06 | Business Intelligence | Mary | New Average Measure in airport alarms | 27568 | Closed Complete | Matthew Broderick | Matthew Broderick | Data Analytics | 5 - Planning | 2023-02-07 12:54 | 8.0711
ENHC0014433 | 2023-01-30 11:10 | 2023-03-07 12:36 | Business Intelligence | Mary | Removal of duplicate Device ID from Alarm data | 27567 | Closed Complete | Matthew Broderick | Matthew Broderick | Data Analytics | 5 - Planning | 2023-05-15 14:37 | 105.1439
ENHC0014405 | 2023-01-20 14:29 | 2023-06-15 10:36 | Business Intelligence | Anthony | Janitor Scan Data into Data Warehouse | 27476 | Closed Complete | Matthew Broderick | Matthew Broderick | Data Analytics | 5 - Planning | 2023-08-02 10:44 | 193.8438
ENHC0014383 | 2023-01-05 13:55 | 2023-02-22 10:02 | Business Intelligence | Mel | New data model using the FIDS/BIDS data | 27417 | Closed Complete | Matthew Broderick | Matthew Broderick | Data Analytics | 5 - Planning | 2023-02-01 14:32 | 27.0255
ENHC0014358 | 2022-12-13 09:20 | 2023-04-26 13:16 | Business Intelligence | Mary | Snow Dashboard: Improvment reqest for materials reporting | 27319 | Closed Complete | Matthew Broderick | Matthew Broderick | Data Analytics | 5 - Planning | 2023-03-29 19:57 | 106.4422
ENHC0014840 | 2023-07-31 13:54 | 2023-09-19 10:43 | Business Intelligence | Steven | Updates to Workday Learning data source | 29145 | Closed Complete | Michael Douglas | Michael Douglas | Data Analytics | 5 - Planning | 2023-08-30 02:07 | 29.5089
ENHC0015314 | 2024-09-09 11:22 | 2024-10-17 01:02 | Business Intelligence | Mary | Crisis Management Source Workflow API Call Proof of Concept/Documentation | 33706 | On Hold | Michael Myers | Michael Myers | Data Analytics | 5 - Planning | 2024-11-16 10:00 | 67.9431
ENHC0015165 | 2024-05-03 08:22 | 2024-10-17 01:02 | Business Intelligence | Anthony | Update SSRS Business Directory Report to be ADA Complaint. | 32323 | On Hold | Michelle Obama | Michelle Obama | Data Analytics | 5 - Planning | 2024-10-24 18:56 | 174.4403
ENHC0015126 | 2024-04-10 10:37 | 2024-09-19 14:10 | Business Intelligence | Rachel | Procurement Opportunities to Flydenver API Gateway | 32064 | Work in Progress | Michelle Obama | Michelle Obama | Data Analytics | 5 - Planning | 2024-04-20 20:44 | 10.4209
ENHC0014954 | 2023-12-04 08:39 | 2024-05-07 00:02 | Business Intelligence | Steven | Updates to Workday data | 30242 | Closed Complete | Michelle Obama | Michelle Obama | Data Analytics | 5 - Planning | 2024-02-26 20:10 | 84.4803
ENHC0014839 | 2023-07-27 11:18 | 2023-12-05 19:27 | Business Intelligence | Anthony | Embed Commerce hub Power BI report in intranet and flydenver.com | 29115 | Closed Complete | Michelle Obama | Michelle Obama | Data Analytics | 5 - Planning | 2024-01-24 16:06 | 181.2001
ENHC0015169 | 2024-05-07 08:23 | 2024-06-11 00:02 | Business Intelligence | Mary | Self Bagdrop Dashboard Enhancement | 32338 | Closed Complete | Nate Bargatze | Nate Bargatze | Data Analytics | 5 - Planning | 2024-09-09 20:51 | 125.5195
ENHC0015114 | 2024-03-26 14:12 | 2024-10-08 15:29 | Business Intelligence | Anthony | Create platform people counter report | 31884 | On Hold | Nate Bargatze | Nate Bargatze | Data Analytics | 5 - Planning | 2024-03-29 06:11 | 2.6658
ENHC0015089 | 2024-03-07 08:22 | 2024-05-07 00:02 | Business Intelligence | Mel | Create new Reporting from aggregated Security Wait Times | 31650 | Closed Complete | Nate Bargatze | Nate Bargatze | Data Analytics | 5 - Planning | 2024-02-25 13:31 | -10.7857
ENHC0015081 | 2024-03-04 08:52 | 2024-03-07 00:01 | Business Intelligence | Anthony | Updates to Passenger and Cargo Analysis Report. | 31608 | Closed Complete | Nina Simone | Nina Simone | Data Analytics | 5 - Planning | 2024-04-21 12:02 | 48.1319
ENHC0015080 | 2024-03-04 08:50 | 2024-03-28 00:02 | Business Intelligence | Anthony | Prep TSA throughput file for Power BI report. | 31607 | Closed Complete | Nina Simone | Nina Simone | Data Analytics | 5 - Planning | 2024-04-10 20:10 | 37.4722
ENHC0014910 | 2023-10-05 17:28 | 2024-01-19 00:01 | Business Intelligence | Anthony | Passenger and Capacity Analysis. | 29794 | Closed Complete | Nina Simone | Nina Simone | Data Analytics | 5 - Planning | 2023-12-02 13:33 | 57.8367
ENHC0015451 | 2024-10-31 08:10 | 2024-10-31 08:10 | Business Intelligence | Steven | Products data cleanup | 34588 | Draft | Rebecca DeMornay | Rebecca DeMornay | Data Analytics | 5 - Planning | 2025-01-04 05:31 | 64.89
ENHC0015450 | 2024-10-31 08:06 | 2024-10-31 08:09 | Business Intelligence | Steven | Alink data to Power BI | 34587 | Draft | Rebecca DeMornay | Rebecca DeMornay | Data Analytics | 5 - Planning | 2024-09-01 07:08 | -60.0406
ENHC0015449 | 2024-10-31 08:06 | 2024-10-31 08:06 | Business Intelligence | Steven | Load Screening data Q3 data | 34586 | Draft | Rebecca DeMornay | Rebecca DeMornay | Data Analytics | 5 - Planning | 2025-02-12 16:06 | 104.3339
ENHC0015048 | 2024-02-08 15:45 | 2024-09-19 14:14 | Business Intelligence | Steven | Connectors Migration | 31264 | Draft | Rebecca DeMornay | Rebecca DeMornay | Data Analytics | 5 - Planning | 2024-06-02 14:19 | 114.9404
ENHC0014775 | 2023-06-12 10:58 | 2024-09-30 14:13 | Business Intelligence | Steven | Upgrade to latest version - Connector 1 | 28806 | Closed Complete | Rebecca DeMornay | Rebecca DeMornay | Data Analytics | 5 - Planning | 2023-08-11 06:35 | 59.8169
ENHC0014602 | 2023-04-10 14:52 | 2024-09-26 12:14 | Business Intelligence | Mary | MS Synapse POC | 28204 | Closed Complete | Rebecca DeMornay | Rebecca DeMornay | Data Analytics | 5 - Planning | 2023-09-13 01:36 | 155.4471
ENHC0014456 | 2023-02-02 11:55 | 2024-04-03 00:01 | Business Intelligence | Steven | Follow up tasks from MS assessment clinic | 27624 | Closed Complete | Rebecca DeMornay | Rebecca DeMornay | Data Analytics | 5 - Planning | 2023-07-06 07:01 | 153.7955
ENHC0014380 | 2023-01-05 12:28 | 2023-06-05 10:56 | Business Intelligence | Steven | Budget form on BI | 27393 | Closed Complete | Renee Russell | Renee Russell | Data Analytics | 5 - Planning | 2023-01-31 05:16 | 25.7003
ENHC0015410 | 2024-10-15 10:36 | 2024-10-30 01:04 | Business Intelligence | Harry | Add a field to the Workday Employee Extract file in the Database | 34347 | Draft | Renee Zellwegger | Renee Zellwegger | Data Analytics | 5 - Planning | 2024-12-13 03:42 | 58.7122
ENHC0015249 | 2024-07-09 10:37 | 2024-09-10 00:01 | Business Intelligence | Mel | AskIT/ServiceNow fields imported into the Data Warehouse. | 32964 | Closed Complete | Renee Zellwegger | Renee Zellwegger | Data Analytics | 5 - Planning | 2024-10-24 12:40 | 107.0855
ENHC0015094 | 2024-03-12 22:58 | 2024-10-25 01:03 | Business Intelligence | Rachel | ADA Monthly Service Reports Automation | 31710 | Closed Complete | Renee Zellwegger | Renee Zellwegger | Data Analytics | 5 - Planning | 2024-06-04 10:02 | 83.4613
ENHC0015179 | 2024-05-14 11:46 | 2024-07-09 00:02 | Business Intelligence | Steven | Maintenance Source rehosting testing | 32416 | Closed Complete | Russell Peters | Russell Peters | Data Analytics | 5 - Planning | 2024-06-18 21:47 | 35.4175
ENHC0014594 | 2023-04-05 15:27 | 2024-04-02 14:17 | Business Intelligence | Anthony | Pull Future Flight Schedules - Data into Data warehouse for reporting. | 28164 | Closed Complete | Russell Peters | Russell Peters | Data Analytics | 5 - Planning | 2023-07-08 08:53 | 93.727
ENHC0014788 | 2023-06-26 09:31 | 2024-03-07 12:23 | Business Intelligence | Steven | Updates to RSJ dashboard | 28875 | Closed Complete | Ryan Reynolds | Ryan Reynolds | Data Analytics | 5 - Planning | 2023-11-25 19:25 | 152.4124
ENHC0014790 | 2023-06-26 09:41 | 2023-10-11 13:36 | Business Intelligence | Steven | Updates to Airline Stats | 28877 | Closed Complete | Sade | Sade | Data Analytics | 5 - Planning | 2023-09-01 21:16 | 67.4829
ENHC0014322 | 2022-11-15 07:57 | 2023-02-13 09:07 | Business Intelligence | Harry | Updates to Airline Dashboard | 27203 | Closed Complete | Scott Bakula | Scott Bakula | Data Analytics | 5 - Planning | 2023-01-26 22:55 | 72.6239
ENHC0015258 | 2024-07-16 09:54 | 2024-09-27 00:01 | Business Intelligence | Steven | Add Search for the Fuel form and process | 33013 | Draft | Steve Martin | Steve Martin | Data Analytics | 5 - Planning | 2024-09-28 12:55 | 74.1255
ENHC0015230 | 2024-06-20 09:52 | 2024-08-02 00:02 | Business Intelligence | Mary | Light Duty Truck PM Report | 32751 | Closed Complete | Steve Martin | Steve Martin | Data Analytics | 5 - Planning | 2024-11-08 01:24 | 140.6476
ENHC0014951 | 2023-12-01 15:07 | 2024-04-03 00:02 | Business Intelligence | Mary | Create Monthly snapshot of MP analytics report (Power BI) | 30240 | Closed Complete | Steve Martin | Steve Martin | Data Analytics | 5 - Planning | 2024-01-18 17:17 | 48.0902
ENHC0014909 | 2023-10-05 17:15 | 2024-07-10 00:02 | Business Intelligence | Mary | Power BI dashboard for Network devices age | 29793 | Closed Complete | Steve Martin | Steve Martin | Data Analytics | 5 - Planning | 2023-11-12 15:39 | 37.9338
ENHC0014884 | 2023-09-07 09:42 | 2023-11-09 19:26 | Business Intelligence | Mary | Materials Management and Fleet Maintenance need assistance making a power BI rep | 29523 | Closed Complete | Steve Martin | Steve Martin | Data Analytics | 5 - Planning | 2023-12-02 00:58 | 85.6357
ENHC0014808 | 2023-07-06 10:56 | 2023-09-19 11:22 | Business Intelligence | Mary | Power BI Help Request (TASK0182200) | 28954 | Closed Complete | Steve Martin | Steve Martin | Data Analytics | 5 - Planning | 2023-12-01 02:39 | 147.6544
ENHC0014766 | 2023-06-06 14:46 | 2023-09-18 14:24 | Business Intelligence | Mary | Po and PR information table info from Maintenance Source in power BI | 28743 | Closed Complete | Steve Martin | Steve Martin | Data Analytics | 5 - Planning | 2023-10-28 00:18 | 143.3969
ENHC0015044 | 2024-02-05 13:51 | 2024-09-19 14:16 | Business Intelligence | Mel | DEN Commercial Dashboard 2.0 | 31231 | Draft | Tina Fey | Tina Fey | Data Analytics | 5 - Planning | 2024-06-03 02:15 | 118.5171
ENHC0015195 | 2024-05-29 08:29 | 2024-10-25 01:03 | Business Intelligence | Steven | Expanding the data that is being passed to us from People Counters via API | 32531 | Work in Progress | Tracy Chapman | Tracy Chapman | Data Analytics | 5 - Planning | 2024-08-13 16:54 | 76.3502
ENHC0015163 | 2024-05-02 13:19 | 2024-06-28 00:01 | Business Intelligence | Mary | Pull data from the vendor into the data warehouse to enable regular reporting on Parking Lot Capacity | 32321 | Closed Complete | Tracy Chapman | Tracy Chapman | Data Analytics | 5 - Planning | 2024-07-23 12:51 | 81.9801
ENHC0015105 | 2024-03-19 14:09 | 2024-03-22 00:01 | Business Intelligence | Steven | I need help creating DPD Shifts (Details) in the CAD Dataset | 31832 | Closed Complete | Tracy Chapman | Tracy Chapman | Data Analytics | 5 - Planning | 2024-06-16 22:31 | 89.349
ENHC0015091 | 2024-03-08 10:14 | 2024-03-08 10:20 | Business Intelligence | Mel | OPs Security Screening Occupancy Reporting | 31651 | Draft | Tracy Chapman | Tracy Chapman | Data Analytics | 5 - Planning | 2024-07-07 12:28 | 121.0933
ENHC0015078 | 2024-03-01 12:57 | 2024-09-19 14:13 | Business Intelligence | Steven | Comms Center Dashboard | 31603 | Work in Progress | Tracy Chapman | Tracy Chapman | Data Analytics | 5 - Planning | 2024-08-07 05:57 | 158.7089
ENHC0015069 | 2024-02-26 14:29 | 2024-09-19 14:13 | Business Intelligence | Steven | Update to Maintenance database | 31483 | Draft | Tracy Chapman | Tracy Chapman | Data Analytics | 5 - Planning | 2024-07-04 14:04 | 128.9827
ENHC0015051 | 2024-02-09 16:38 | 2024-09-19 14:14 | Business Intelligence | Steven | Connect to an external weather dataset for our Snow Dashboards probably via API to help our team better tell the story about runway downtime. | 31266 | Draft | Tracy Chapman | Tracy Chapman | Data Analytics | 5 - Planning | 2024-02-21 23:04 | 12.2682
ENHC0015259 | 2024-07-16 11:27 | 2024-09-19 12:45 | Business Intelligence | Mary | Non-Production Network Production/Inventory Values and Cost Estimation sheets need adjusting/correcting (use attached docs) | 33034 | Draft | Travis Barker | Travis Barker | Data Analytics | 5 - Planning | 2024-07-18 05:39 | 1.7588